Annex A – UNDAF Results Matrix

| UNDAF Priority 1: Peace Security and Rule of Law |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| National Development Goal: To improve the quality of life of the Liberian people and promote sustainable and equitable socio economic development by ensuring a secure environment where peace and the rule of law of are upheld. UNDAF Outcome Group Peace Security and Rule of Law Goal: to create an atmosphere of peaceful co-existences that is conducive to reconciliation and conflict resolution ensuring that security, access to justice, and rule of law are guaranteed |  |  |  |  |  |
| Outcomes/Outputs | Indicators, Baselines, Targets | Means of Verification | Risks and Assumptions | Role of Partners | Indicative Resources |
| Outcome 1.1: Rule of Law: Liberia has an improved, inclusive Rule of Law framework for effective administration of and equitable access to justice in compliance with International Human Rights Standards | % of cases reported to the statutory and customary justice system (disaggregated by age, gender and type of case (SGBV)) Baseline: Civil cases: 3% formal, 38 % informal and 59% to no forum at all. Criminal cases: 2% formal, 45% informal, 53 no forum at all. Target: 23% for formal justice?? % of reported cases disposed of (disaggregated by age, gender and type of case (SGBV)). Baseline: -SGBV cases: 4% Other Cases: 3% No age disaggregated data available Target: 2014 – 20%, 2017- 50% # of pre-trial detainees (disaggregated by age, sex and county) Baseline: 1393 Target: 2014: 700, 2017 - 400 Level of compliance of the customary and statutory justice systems with international human rights standards. TBD: Scale measure of compliance with IHR will be developed and used for all relevant indicators Effective oversight and accountability mechanisms exist in rule of law institutions at all levels. Baseline: MoU between police and prosecution Target: Justice and Security institutions within the Hub complex – Gbarnga 2013 and Zwedru - 2017 RoL Institutions with capacity to effectively administer justice at regional, county and district level – disaggregated by the ratio of judges, magistrates, judicial officers, prosecutors, public defenders, correction and probation officers Baseline: TBD Target: Justice and security institutions within the Hub Complex (Criminal courts, prosecution, police, immigration, corrections, probation) Integrated record keeping and case management system established and functioning in 3 Hubs Baseline: 0 Targets: 2 regional hubs (6 counties) | MoJ and Judiciary reports UNMIL/UNCT reports Population survey Legal analysis UNPOL Crimes Statistics | Risks: - Lack of GoL budgetary support for the RoL sector - Lack of adequate bi- and multi-lateral sector funding for RoL sector reform - Strong traditional beliefs, values, practices and gender stereotyping could hamper compliance with IHR standards - Lack of GoL political will for reform, notably by the Judiciary - Separation of Powers not complied with. - Security problems escalate distracting from reform and development agenda. Assumption: - UNCT and UNMIL work in a coherent manner and deliver as one. - UNDAF is properly aligned to the PRS. - GoL pursues a reform agenda and has the capacity to deliver reforms. - Independence of National Commissions is respected by various branches of government - GoL will have adequate capacity, resources and commitment to sustain programme achievements. - Civil society groups and CSOs are able to effectively represent community and group interests and resist government and donor pressure. |  |  |
| Output 1.1.1: Legal framework on harmonization of customary and statutory justice systems developed in compliance with IHRS. | Existence of legal framework document Baseline: 0 / Target: 1 Existence of scale of measure for compliance with IHR Baseline:0/Target:1 | Legal framework document |  |  |  |
| Output 1.1.2: INCHR strengthened to implement its mandate to improve the Human Rights situation. | # of human rights monitors trained and deployed to all counties Baseline: 0 / Target: 15 (at least 30% women) # of HR violations reported and addressed (disaggregated by age, sex, type) Baseline: TBD / Target: 100% Existence of reporting mechanism and capacity in place Baseline: 0 Target: quarterly reporting | INCHR reports CSO reports UNMIL/UNCT reports |  |  |  |
| Output 1.1.3: Enhanced protection of 1.1.3 Enhanced protection of vulnerable groups in the justice system, including women, children and persons with disabilities. | Proportion of reported cases of GBV successfully prosecuted (disaggregated by age, sex, disability, county) Baseline –4% Target- 50% Proportion of reported cases of violence against children successfully prosecuted (disaggregated by age, sex, disability, county) Baseline: 10% Target: 30% Number of survivor/child-friendly witness and victim protection services at regional level Baseline: 0 Target: 5 | MoJ reports Judiciary Reports MoHSW Reports MoGD Reports GBV IMS System MoJ SGBV Crimes Unit Report |  |  |  |
| Output 1.1.4: Improved application of IHR standards and principles through domestication and treaty reporting | # of key IHR instruments ratified Baseline Target: Optional Protocols to CRC on involvement of children in armed conflict and on the sale of children, child prostitution and pornography to be ratified # of ratified IHR instruments domesticated Baseline: CRC domesticated Target: Optional protocol ; CEDAW???????domesticated Baseline: and domesticated. To be completed # of treaty reports submitted timely Baseline: CRC 2nd, 3rd and 4th combined report submitted in 2009, CEDAW report submitted 2009 To be completed Target: CRC and CEDAW report submitted in 2013 | National Gazette Treaty Body reports |  |  |  |
| Output 1.1.5: Improved public knowledge of legal rights and remedies for access to justice | #% of survivors accessing justice services (disaggregated by county and district) Baseline: 35% Target: 50% Change in public perception of justice system (disaggregated by age, sex, and county). ( Can UNDP allocate money for survey) | MOJ IMS Reports MOGD IMS MOHSW IMS |  |  |  |
| Output 1.1.6: Service delivery capacity of the rule of law institutions improved at county and district levels. Output 1.1.7: Increased institutional and professional capacity of rule of law institutions to effectively administer justice. | # of logistic support facilities provided, renovated, upgraded and/or constructed (disaggregated by type, institution, geographic location) Baseline: 1 regional hub Target; 5 REGIONAL HUBS # of Justice sector professional trained (prosecutors, public defenders, judges, court officers, investigators, police disaggregated by role, gender, age, geography, etc.) Baseline: Data from JTI (2012) Target: at 50% of all Justice sector professionals trained | Project reports MoJ Reports ToJ Reports UNMIL reports |  |  |  |
| Outcome 1.2: Peace and reconciliation: Liberia has an improved, coherent and inclusive mechanism for national reconciliation operationalized at national, regional county and local level. | % of disputes successfully resolved by ADR mechanisms (disaggregated by county, gender, age, ethnicity and type of conflict) Baseline: TBD: Land Commission, MoYS# of relevant TRC recommendations effectively implemented Baseline: TRC report Target: recommendations on inclusiveness, participation and decentralisation adopted Change in perception of national identity and belonging (disaggregated by gender, age, ethnicity and geography). Baseline: PBO LPP M&E unit Target: Curriculum on peace education and human rights for schools | PBO LPP M&E reports Land Commission, MoI, MoYS, County reports MOEIMS reports | Risks: Lack of GoL budgetary support for national reconciliation Lack of adequate bi- and multi-lateral sector funding for national reconciliation Vulnerable and marginalized groups lack confidence in national reconciliation process. Lack of GoL political will for profound and genuine reconciliation process. High level of political and economic marginalization among youth. Internal and trans-border security problems escalate undermining social cohesion. Charles Taylor (verdict / return). Assumptions: UNCT and UNMIL work in a coherent manner and deliver as one. UNDAF is properly aligned to the PRS. GoL pursues an inclusive reconciliation agenda and has the capacity to deliver on key reconciliation priorities. Independence of National Commissions is respected by various branches of government GoL will have adequate capacity, resources and commitment to sustain programme achievements. Civil society groups and CSOs are able to effectively represent community and group interests and resist government and donor pressure. |  |  |
| Output 1.2.1: National reconciliation strategy developed with active participation by and consideration of marginalized and vulnerable populations. | Effective national coordination structure for reconciliation put in place Baseline: Palava /Peace Hut mechanism Target: More inclusive, integrated coordination structure exists % of representatives from vulnerable and marginalized groups involved in strategy development from initiation to completion Baseline – n/a Target – 30% | INCHR monitoring Local Government reports Consultation reports CSO reports Population survey TAG reports |  |  |  |
| Output 1.2.2: ADR mechanisms formalized and operationalized at all levels in accordance with IHR principles. | # of functioning ADR mechanisms (disaggregated geographically) Baseline: 15 Peace Committees? Target: 88 Peace Committees Formal ADR Framework developed Baseline – 0 Target - 1 | Local government reports CSO reports UNMIL monitoring information ADR Framework document Land Commission, PBSO |  |  |  |
| Output 1.2.3: Increased capacity of INCHR and civil society to advocate for national reconciliation and implementation of relevant TRC recommendations. | # of public fora held by CSOs on national reconciliation Baseline: N/A Target: TBD??????? | CSO reports INCHR reports Population survey |  |  |  |
| Output 1.2.4:Integrated curriculum and increased understanding among children, youth and general public of peace, tolerance and national identity. | Human Rights and Civics curriculum exists # of schools teaching civic education and history of Liberia ( Ensure linkage Human Development Outcome Group) # of functioning community based resource centers providing peace building information and activities Baseline: 0 Target: 15 | National curriculum MoE statistics |  |  |  |
| Outcome 1.3: Security: Liberia has more efficient, effective, accountable and responsive security institutions at the national, regional, county and local levels | # of LNP officers deployed in Monrovia and County police stations disaggregated by sex and rank (Baseline: 2,035; Target: 3,535) # of BIN official border crossings fully staffed and fully operational (Baseline:0; Target:36) # of LNP Strategic Plan projects completed: Baseline: 40; Target: 140 # of BIN Strategic Plan projects completed: Baseline: 2, Target 101 # Number of National Security Council meetings convened (Baseline: 6 per year; Target 12 per year). % increase in national budgetary allocations for security sector institutions(Baseline: FY11/12: Annual Budget (LNP, BIN) Target: 20% per subsequent year minimum % of civilian complaints registered with LNP which are investigated by LNP Professional Standards Division and final disposition decided (Baseline: 2011: 156 registered/18 disposed – 12%) Target: 75% minimum disposal rate achieved and sustained Proportion of human rights violations and non-compliance cases reported, and addressed across all security sector institutions (disaggregated by age, gender and type). Baseline: Proportion of human rights violation reported and are addressed (UNMIL-HRPS ) Target: Proportion of human rights violations reported and are addressed through IHRC- IMS | LNP Annual Plan and internal records National Budget LNP Professional Standards Division registers Regional Hub Referral Office records Minutes from the Justice and Security Board meetings UNMIL HRPS SIT REPS IHRC Reports | Risks: Lack of GoL budgetary support for the security sector. Lack of adequate bi- and multi-lateral sector funding for SSR. Strong traditional beliefs, values, practices and gender stereotyping could hamper compliance with IHR standards. Lack of GoL political will for security sector reform. Internal and trans-border security problems escalate putting pressure on limited resources and undermining social cohesion. Charles Taylor returns to Liberia. Assumptions: UNCT and UNMIL work in a coherent manner and deliver as one. UNDAF is properly aligned to the PRS. GoL pursues a reform agenda and has the capacity to deliver reforms. GoL will have adequate capacity, resources and commitment to sustain programme achievements. Civil society groups and CSOs are able to effectively represent community and group interests and resist government and donor pressure. Security institutions perform professionally and attract sufficient public trust. |  |  |
| Output 1.3.1: Identified critical security gaps filled | # of LNP Police Support Unit Officers trained and deployed in regions and counties (Baseline 70, Target: 600) # Number of regular LNP officers vetted, recruited, trained and deployed per year increased (Baseline 300: Target: 600 minimum per year) # of prisons fully staffed with trained corrections officers Baseline: 1 Target: 14 % of BIN officers trained and deployed Baseline:521 of 1680 officers – 31%, Target: 100% Corrections Response Unit established and deployed ( Baseline: 0 target 78) % of UNMIL security functions identified in Joint Transition Plan taken on or resolved by Government security agencies or other agreed means: Baseline: 0%, Target: 100%) % of GoL fiscal budget for security sector Government to increase financial support for security sector (Baseline: 4.9% of GDP, Target: 6% of GDP) | UNPOL Planning Department Report PBF-L Status Reports JSJP Reports SSR and USAID Reports (AFL) GoL reports RBB Reports Security Agency Budgets and Annual Reports UNSG Report April 2012 (TAM report) Government of Liberia-UNMIL Transition Planning Worksheets Annual budgetary submission from the Ministry of Finance to the Legislature |  |  |  |
| Output 1.3.2:Regional Hubs in place with capacity to deliver services | # of hubs fully operational (Baseline: 0, Target 5) # of hubs effectively operational (Baseline: 70% of staff deployed, plus plan in place to phase in recurring costs) % of population with the coverage area aware of and accessing services provided by the hub (disaggregated by age, gender and county) | PBF-L reports JSJP reports CSO reports UNMIL & UNCT reports MoJ reports Judiciary reports Reports by PBO to the PBF Joint Steering Committee World Bank/UNMIL policy note on security sector public finance management |  |  |  |
| Output 1.3.3: Security Sector oversight, accountability and management structures enhanced | Change in public confidence in security agencies and institutions (Baseline: 30 – 40 %, Target: 90 – 100%) # of public hearings by Legislature on security sector issues Target: Four critical security sector bills endorsed, namely police bill, prison bill, drugs control bill and gun control bill. Security Sector Civilian Oversight Mechanism established # of public officials prosecuted on charges related to corruption Baselines: MICS tbd Targets: A prison oversight and monitoring mechanism established (Baseline Nil) | UNPOL Planning Dept Reports JSJP Reports Security Agency reports MICS Legislative Reports Population survey Reports by Security Sector Civil Society Working Group Reports by the Armed Violence Observatory |  |  |  |
| Output 1.3.4:IHR standards effectively institutionalized in all Security Sector institutions | # of security sector institutions with HR, Gender, Child Protection, Human Trafficking and HIV/AIDS training and Professional Standards institutionalized Baseline: Target: # of reported, investigated and addressed HR violations (disaggregated by institution) | Institutional HRMS and training reports Professional Standards bodies reports MoJ reports Judiciary reports Reports by new security sector civilian oversight mechanism Reports by INCHR monitors |  |  |  |
| Output 1.3.5: Enhanced female empowerment in security sector institutions | Gender-sensitive Human Resource Policy in place for all security sector institutions. 20% female representation achieved and sustained within security agencies (Baseline: LNP 17.3%; Target: 20%)Level of women’s recruitment, retention, training and promotion in security sector institutions 20% female representation in within each rank structure of security sector agencies (Baseline TBD) Baseline: 2012 - LNP & BCR have draft Target: HR Policy | Training academies’ reports HRMS reports MoJ reports MoD reports Judiciary reports UN Women |  |  |  |

| UNDAF Priority 2: Sustainable Economic Transformation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| National Development Goal: to transform the economy to meet the demands of Liberians by leveraging the FDI in mining and plantations to develop the domestic private sector; provide employment for youthful population; invest in infrastructure for economic growth; address fiscal and monetary issues for macroeconomic stability ; and improve agriculture to expand the economy for rural participation and food security |  |  |  |  |  |
| Outcomes/Outputs | Indicators, Baselines, Targets | Means of Verification | Risks and Assumptions | Role of Partners | Indicative Resources |
| Outcome 2.1: Improved sustainable Natural Resource Utilization and food security | I: Prevalence of food insecurity, disaggregated by sex and geographic area B: Liberia: 41%; Rural: 57%; Urban: 18%; Rural Female headed households: 63.3%; Rural Male headed households: 56% Targets? reduced I: Domestic production of staple food commodities , Baseline: Paddy rice: 296,090 MT.; Fresh cassava tubers 493,000 MT. ; fish……. I: Annual quantity of staple cereal (rice ) imported Baseline: milled rice 242,567 MT Post-harvest loss of staple cereal crop (rice) Baseline: 40% Target: 10% | Agricultural production statistics (livestock, crops, fisheries), MoA / LISGIS CFSNS Trade statistics, MoCI / Central Bank Source: MoA /LISGIS Agricultural Production Survey Source: Liberia Labour Force Survey 2010 Source: MoA crop production statistics Source: MoA/LISGIS Agricultural production survey | RISKS Insufficient government and private sector investment in agriculture; Inflation and increasing food prices; Adverse climatic variations affect production; Inadequate capacity of the Government of Liberia and local communities to effectively implement agriculture and food security strategies and programmes. ASSUMPTIONS Sustainable food security remains a key priority in Government of Liberia’s development strategies; Infrastructure development, including for transport and marketing, meets the targets in the PRS 2 and leads to lower costs of production; Land tenure system supports agricultural production. | GOL and UN |  |
| Output 2.1.1: Agricultural production and productivity of small holder farmers increased and diversified | Annual yields of staple food crops on smallholder farms Baseline: Rice- 1.18 MT/ Hectare cassava 8.01 MT/Hectare Target : Rice---2.5 MT/ Hectare cassava 10.0 MT/Hectare Average number of livestock and poultry owned by smallholder household by type Baseline Livestock: Goats 3 ; Pigs 3 Poultry: Chicken 7 Target Livestock: Increased Poultry: Increased Number of fish ponds in selected target areas (MOV: MoA production statistics, monitoring) Baseline: 500 Target: Increase (TBD) Size of smallholder farms by type of crops (rice, cassava ) ) Baseline : Rice- 1.0 hectare Cassava- 0.5 hectare Target: Rice - Increase Cassava- Increase Hectares of irrigated lowland areas rehabilitated /developed in target areas Baseline: 1,100 Hectares Target: 2,500 Hectares Proportion of smallholder farmers with access to improved inputs, in particular, high yielding rice varieties Baseline : 9% Source: Target: Increase (TBD) | Source: MoA /LISGIS Agricultural production survey Source: MoA/LISGIS Agricultural production survey Bureau of Fisheries Source: MoA/LISGIS Agricultural production survey JP FSN Reports Source: MoA/LISGIS Agricultural production survey |  |  |  |
| Output 2.1.2: Value-added post-harvest food processing and market linkages for small holder farmer organizations expanded | Number of small holder farmers organizations (disaggregated by type of membership eg. women groups, youth groups, etc.) supported to acquire and utilize food processing technology in target areas Number of food processing facilities established by smallholder farmer organizations (disaggregated by type of membership eg. women groups, youth groups, etc.) in target areas Baseline: (i) mixed cooperatives- 5 (ii) women groups - 6 and youth groups- 0 Target: (i) mixed smallholder cooperatives- TBD (ii) women farmer organizations - TBD and youth farmer organizations- TBD Number of smallholder farmer organizations (disaggregated by type of membership eg. women groups, youth groups etc.) assisted to participate in competitive tenders to supply food commodities to selected market development programmes (eg. P4P) Baseline: 5 Target: 20 Metric tons of processed food commodities (rice, beans, cassava flour) sold by farmer organizations through selected market development programmes (eg P4P) Baseline: 800 Target: 2,500 | JP FSN Reports JP FSN Reports JP FSN Reports JP FSN Reports |  |  | UN Women |
| Output 2.1.3: Productive safety-nets with focus on smallholder youth and women farmers expanded in selected target areas | Number of women and youth farmers participating in labor intensive agriculture workfare schemes in target areas Baseline: 19,500 (WB & WFP) Target: 80,000 (??) Number of women and youth benefiting from agricultural inputs distribution, grants and loan schemes in target areas Baseline: Target Number of community grain reserves (CGRs) established in target areas Baseline: 0 Target: 15 | JP FSN Reports and WB |  |  | UN Women: |
| Output 2.1.4 Utilization of Natural Resources (land, water and forest) improved | Hectares under slash and burn ,shifting cultivation upland farming systems in target areas Baseline TBD Target: TBD Hectares of land under irrigated lowland farming systems Baseline : 3,000 Target: TBD Number of communities assisted to adopt sustainable forest resources management practices Baseline: TBD Target : TBD Number of communities assisted to adapt and mitigate the effects of climate change Baseline: TBD Target |  |  |  |  |
| Output 2.1.5: Capacities of public and community level institutions to coordinate, deliver and monitor food security programmes increased | Number of quality agricultural production survey reports produced per year Baseline: 1 Target: 1 Number of food security and vulnerability assessment reports produced Baseline: 1 every 2 years Target: 1 every year Number of farmer based organizations (disaggregated by type of membership eg. women groups, youth groups etc.) assisted to deliver extension services Baseline: 11 Target: 25 Number of food security and natural resources focused Public Institutions provided with technical and material support. Baseline: 4 Target: 4 Average number of agricultural extension officers , disaggregated by sex, per county Baseline : TBD Target; TBD | JP FSN reports JP FSN reports |  |  |  |
| Outcome 2.2: Rural and urban Liberians have improved equal access to sustainable livelihoods opportunities in an innovative and competitive private sector for rural and urban areas. | Labour force participation rate, disaggregated by sex, age and geographic area B: Liberia: 62.8%; Urban: 54.9%; Rural: 71.2%; Male: 66.1%; Female: 59.9%; Youth: TBD T: Proportion of Liberians in vulnerable employment, disaggregated by sex, age and geographic area B: Liberia: 77.9%; Urban: 67.5%; Rural: 86.1%; Male: 68.3%; Female: 87.3%; Youth: TBD T: Proportion of paid employees, employers and members of producers’ cooperatives in total employment, disaggregated by sex, age and geographic area B: Liberia: 21.1%; Urban: 41.6%; Rural: 12.8%; Male: 31.2%; Female: 11.1%; Youth: TBD T: Liberia: 30%; Urban: 45%; Rural: 20%; Male: 35%; Female: 20%; Youth: TBD Proportion of Liberian workers in the informal sector B: Liberia: ; Urban: ; Rural: ; Male: ; Female: ; Youth: T: Liberia: ; Urban: ; Rural: ; Male: ; Female: ; Youth: TBD Percentage of workers in agriculture, forestry and fishing in vulnerable employment, disaggregated by sex and age B: Liberia: 94.1%; Male: 91.9%; Female: 96.2%; Youth: TBD T: Percentage of Liberians who have completed vocational training, disaggregated by sex, age and geographic area B: Liberia: 14.2%; Urban: 18.2%; Rural: 9.8%; Male: 18.7%; Female: 10.2%; Youth: TBD T: Liberia: 20%; Urban: 21%; Rural: 13%; Male: 20%; Female: 15%; Youth: TBD Number of registered MSMEs, disaggregated by sex, ownership and geographic area B: 8369 businesses registered with LBR (7,200 are Liberian owned, 1169 are foreign businesses) and 388 petty traders registered; disaggregation to be completed by 2013 T: Target to be set according to PRS 2 target for GoL Ease of doing business B: Number of days to start a business: 9 days; Cost as % of income per capita: 68.4% T: Target to be set according to PRS 2 target for GoL Evidence and existence of the implementation of HIV and AIDs policies and programmes in the work place B: National HIV/Aids Workplace Policy adopted; National Rubber Sector HIV and AIDs Work Place policy pending T: Extent to which the Decent Work Bill has been implemented B: T: A streamlined private sector regulatory framework with standardized enforcement mechanisms in place B: T: | Liberia Labour Force Survey 2010, CWIQ 2010, and Liberia Population and Housing Census 2008 Liberia Labour Force Survey 2010, CWIQ 2010, and Liberia Population and Housing Census 2008 Liberia Labour Force Survey 2010, CWIQ 2010, and Liberia Population and Housing Census 2008 Liberia Labour Force Survey 2010, CWIQ 2010, and Liberia Population and Housing Census 2008 Liberia Labour Force Survey 2010, CWIQ 2010, and Liberia Population and Housing Census 2008 Liberia Labour Force Survey 2010, CWIQ 2010 Liberia Business Registry WB Doing Business Survey Ministry of Labour; NAC Ministry of Labour NIC, MoCI, MoL, MoF | RISKS Corruption and rent seeking behavior is not sufficiently addressed; Inflation; Low liquidity within the financial sector; Slow growth of the private sector leads to skilled labor supplies exceeding demands; Costs of formalization outweigh the expected benefits for micro enterprises. ASSUMPTIONS Government remains committed to inclusive growth, anchored on the private sector, and demonstrates ownership of the reform mechanisms; Infrastructure development, including for transport and energy, meets the targets in the PRS 2 and leads to lower costs of production; Concessionaires remain committed to adhere to practices of corporate responsibility outlined by the Corporate Responsibility Forum; Decentralization of banking services and continued commitment from the Central Bank to the expansion of financial services in rural areas. |  |  |
| Output 2.2.1:Strengthening partnership between SMEs, formal private sector and government for employment creation (SME development and partnership for employment creation) | Number of members admitted to the Corporate Responsibility Forum B: T: Existence of public / private dialogue within the Liberia Development Alliance B: N T: Y Proportion of labour market transforming into skilled employment; Number of apprentice especially youth finding placement in private sector | Corporate Responsibility Forum |  |  |  |
| Output 2.2.2: Mechanisms developed to streamline the regulatory framework for the private sector, including standardization of enforcement mechanisms by 2017. | Comprehensive strategy to enhance the competiveness and promotion of the private sector available B: N T: Y Number of Government agencies carrying out inspections per month B: 13 T: 6? Existence of an ISO Certified National Standards Lab B: N T: Y Existence of coordinated and standardized enforcement mechanisms for commercial contracts and concession agreements B: N T: Y | NIC and MoCI NIC and MoCI MoCI MoCI, NIC, Commercial Court, MoF |  |  |  |
| Output 2.2.3: | Number of Liberians in the informal sector represented by organized labor or union associations B: TBD with MoL T: Number of enterprises belonging to a employer organization B: TBD with MoL T: Number of entities implementing HIV and Aids policies in the work place, disaggregated by sector; B: TBD with MoL T: Number of child labour cases identified and investigated by the Ministry of Labour; B: TBD with MoL T: Number of collective bargaining agreements reached between the Tripartite partners B: TBD with MoL T: | Ministry of Labour |  |  | UN Women: |
| Output 2.2.4: Increased business access to quality vocational training and business development services for targeted groups of youth, women and differently-abled persons, including in the agricultural sector by 2017. | Number of youth, women and differently-abled persons graduating from quality vocational training and business skills training, disaggregated by sex, age and geographic area |  |  |  | UN Women: |
| Output 2.2.5: Business upgrading and Increased access to financial services and entrepreneurial skills for MSMEs, towards value chain development, particularly in the rural areas and including for the agricultural sector by 2017. | Number of microfinance clients, disaggregated by sex and geographic area B: TBD with Central Bank Liberia T: Diversity of financial products available through formal institutions, disaggregated by size of loans, targeted clients and geographic area B: TBD with Central Bank Liberia and MoCI T: Number of women and men accessing financial services through Village Savings and Loan Associations B: TBD with Central Bank Liberia T: |  |  |  | UN Women: |
| Outcome 2.3: Improved access to sustainable basic infrastructure | - Kilometers of secondary feeder roads - Proportion of urban population living in planned settlements - Percent of households with access to electricity and / or renewable energy sources, disaggregated by sex of hh head and geographic area (10% in Monrovia, 2% in rural areas) | - MoPW report of new feeder roads - Number of planned settlement inhabited - LISGIS, Liberia Population and Housing Census 2008 and local government authorities - Liberia Population and Housing Census 2008 | RISKS Non-exoneration of alternative energy products from customs duties makes products unaffordable for public consumption; Domestic skills not adequately developed to meet the needs for infrastructure construction; Interventions for improving housing conditions for the poor benefit high income earners; Liberian private sector too weak to support infrastructure development. ASSUMPTIONS Government remains committed to improving housing conditions for the urban poor; Cost of grid electricity continues to decline; Policy frameworks is endorsed by the Government of Liberia; | WB, UNOPS, UN HABITAT, UNDP, UN Women; FAO, UNMIL and GoL |  |
| Output 2.3.1: National Urban Development strategy and legal framework prepared and capacities strengthened for implementation by 2017. | - National urban development strategy and legal framework in place - Number of Urban Development plans prepared by 2017. Target: 10 | MoPW, MLME, NHA, LWSC and LEC annual report |  |  |  |
| Output 2.3.2: Policy framework developed for increasing access to adequate and affordable housing and capacity of National Housing Authority strengthened for implementation by 2017 | - National Housing Policy is available - Number of staff at NHA trained in housing policy development and implementation - Increased allocation of public housing to the poor and low income earners | NHA annual report MoPW data/report NHA and MoPW annual report |  |  |  |
| Output 2.3.3: Agricultural and marketing infrastructure expanded. | - Number of gender-sensitive market facilities constructed - Number of warehouses constructed - Kilometers of secondary feeder road and bridges rehabilitated / constructed, including plans for their maintenance | Liberia Produce and Marketing Corporation (LPMC), MoA, Farmers Corporative annual report MoPW and MoA annual report |  |  | UN Women: |
| Output 2.3.4: Enhanced capacities of national agencies for on grid and off grid electricity provision, with particular focus on providing alternative energy sources to rural communities, by 2017. | - Existence of a master plan for Rural and Renewable Energy in Liberia - Number of targeted rural communities accessing affordable and reliable alternative energy sources | Rural and Renewable Energy Agency (RREA) of Liberia RREA data and annual report |  |  | UN Women: |
| Outcome 2.4: Evidence-based policies to maintain s a stable and inclusive macro-economic environment | - Availability of official, sex disaggregated data at national, sectoral and county levels; - Source: LISGIS and National Strategy for Development Statistics - Frequency of national surveys (CWIQ, National Accounts); - Source: LISGIS and National Strategy for Development Statistics - Proportion of national, sectoral and local development policies and programmes formulated using data and statistics, integrating population factors and disaggregated by sex; - Source: LISGIS and MoPEA - Proportion of national plans and projections informed by macroeconomic models and tools - Source: MoF - Existence of a gender-responsive budgeting framework at national and local government levels; - Source: MoF and MoGD - Liberia’s ECOWAS import source penetration ratio - Source: MoCI Baseline: 16-20% - Proportion of Liberia’s tariffs aligned with ECOWAS common external tariff - Source: MoF, National Coordinating Committee on the Common External Tariff (NCC-CET) - Evidence of corruption and rent-seeking behavior as a barrier to trade - Source: Annual report of ECOWAS Secretariat |  | RISKS Unanticipated shocks due to changes in the dual currency regime; Outbreaks of crisis within the region threaten economic trade integration; Inflation; Government staff turnover threatens the sustainability of capacity and institutional strengthening measures. ASSUMPTIONS Government remains committed to sound macro economic management and performance; Government and Legislature remain committed to gender equality in planning and budgeting; National Strategy for Development Statistics remains operational and effectively coordinates data collection and analysis; Demonstrated commitment of other ECOWAS countries for regional economic cooperation and integration. |  |  |
| Output 2.4.1: Enhanced national and local capacities for data collection, analysis and utilization towards effective socio-economic surveillance and monitoring development results, including the MDGs, by 2017 | - Number of national technical staff successfully completing formal training courses on data management; - Number of national technical staff successfully completing formal training courses on integration of population factors into development planning - Number of national reports / databases made available by LISGIS and national bodies - Strength/quality of Debt sustainability Capacity within the MOF - Financial reporting by SOEs |  |  |  |  |
| Output 2.4.2: Enhanced capacities for macro-economic modeling and policy research, development and advocacy by 2017. | - Number of technical reports produced by GoL Economic Management Team utilizing macroeconomic simulation models - Existence of informed economic analysis within the system of National Accounts - Frequency of the collection of Balance of Payments data and Government’s finance statistics - Number of institutions engaged in policy advocacy and policy research - Effectiveness/state of capacities for macro-economic modeling and policy research, development and advocacy by - Extent of NSDS roll-out - Published reports of a national policy analysis and research think thank |  |  |  |  |
| Output 2.4.3: Strengthened capacities for fiscal and monetary policy management, including in gender responsive budgeting with focus on financial systems automation, soundness of fiscal policy, debt management and efficacy and transparency of spending, by 2017. | - Existence of published fiscal monetary information including analytical reports on the National Budget performance - Investment and debt in structure of public spending-including skewness of public spending - Tax administration, fiscal planning and debt sustainability capacity - Wage bill to GDP, revenue and expenditure - Price index and exchange rate - Debt sustainability(lowness of public debt) - Revenue Collection and sustainability of the structure of public debts. - Existence of a Value added tax regime - Gender Responsive Budgeting incorporated into the Medium Term Expenditure Framework |  |  |  | UN Women: |
| Output 2.4.4: Strengthened national framework for regional and global economic cooperation and integration towards macroeconomic harmonization and convergence by 2017, with focus on international trade | - Existence of a functioning National Coordinating Committee on Multilateral Surveillance - A Harmonization and Transition Plan on CET available - Proportion of intra-regional trade in total ECOWAS trade - Trade orientation and import source penetration ratio - Existence of a HS Code that is consistent with World Customs Organization Classification and ECOWAS CET - Drafting of national plans for the removal of tariff and nontariff barriers to trade |  |  |  | UN Women: |

| UNDAF Priority 3: Human Development |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| National Development Goal: to improve quality of life by investing in: quality education; affordable and accessible quality health care; social protection for vulnerable citizens; and equitable access to environmentally friendly water and sanitation services. |  |  |  |  |  |
| Outcomes/Outputs | Indicators, Baselines, Targets | Means of Verification | Risks and Assumptions | Role of Partners | Indicative Resources |
| Outcome 3.1 Health and Nutrition The population has increased access to and utilization of equitable, affordable, and quality health and nutrition services. | % of health facilities achieving two-star level of EPHS accreditation Baseline: 9% Target: 90% Proportion of deliveries with skilled birth attendants. Baseline: 22% Target: 40% % of Health Centers and Hospitals providing functional emergency obstetric and neonatal care services. Baseline: 38% Target: 65% Contraceptive prevalence rate (CPR) and unmet need CPR Baseline: 11% CPR Target: 16% Unmet baseline: 36% Unmet target:18% Proportion of f children who received Penta-3 Baseline: 73% Target: 90% Proportion of infants (0-6 months) exclusively breastfed Baseline: 34% Target: 50% | EPHS Accreditation report HMIS, CWIQ and DHS EmONC Assessment LDHS, HMIS , LDHS, HMIS | Assumptions Increased resources allocation for implementation of EPHS National Health human resource plan effectively implemented Supply chain and logistics management system effective Road Map on Maternal and Newborn health is fully implemented Maternity legislation and Code of Breastmilk Substitutes Code enacted Risks Lack of adequate fulfillment of donor commitments Food security, food prices and livelihood situation deteriorates Planning, management and monitoring capacity not adequately enhanced | MOH&SW MOFDP MODG LISGIS UNICEF UNFPA WHO UNHCR WB WFP UNAIDS NGOs |  |
| Output 3.1.1 Strengthened national capacity to provide comprehensive maternal and newborn health services with emphasis on most vulnerable and marginalized communities in compliance with national policies | Proportion of health facilities with functioning referral systems Baseline: 70% Target: 90% Proportion of health facilities providing youth- and adolescent-friendly SRH services according to standards Baseline: 15% Target: 50% Proportion of counties reporting maternal and neonatal deaths within 48 hours. Baseline: TBD Target: 60% Percentage of BEmONC facilities with communication system in place Baseline: 30% Target: 90% Proportion of Health Facilities implementing the Road Map for Reduction of Maternal and Newborn Mortality according to the standards. Baseline: Target: | EPHS accreditation Report HMIS, HMIS Report, HMIS Report EPHS accreditation Report |  | MOH&SW MOFDP MODG LISGIS UNICEF UNFPA WHO UNHCR WB WFP UNAIDS NGOs |  |
| Output 3.1.2 Maternal Health Women and adolescents have increased awareness and knowledge related to maternal and newborn health care information and services. | Proportion of women and adolescents who have knowledge in Maternal, Newborn, and Child Health care and immunization issues. Baseline: TBD Target: Proportion of newborns breastfed within one hour of birth Baseline: 34% Target: 60% Proportion of health facilities with functional Community Health Development Committee (CHDs). Baseline: Target: 30% | KAP Survey KAP Survey, EPI Survey HMIS, EmONC Assessment |  | MOH&SW MOFDP MODG LISGIS UNICEF UNFPA WHO UNHCR WB WFP UNAIDS NGOs |  |
| Output 3.1.3 Capacity of Ministry of Health and Social Welfare strengthened to implement and monitor EPHS at all levels within Human Rights framework | Proportion of population within 5km of health facility. Baseline: 69% Target: 85% Proportion of transfused blood that meet national standards Baseline: Target: 100% Proportion of health facilities with functioning diagnosis for basic investigation including HIV-AIDS, B and Malaria Baseline: Target: 85% Proportion of health facilities providing timely, accurate and complete HIS reports to the MOH&SW. Baseline: 76% Target: 90% Proportion of national budget allocated for heath and social welfare Baseline: 7.8% Target: 15% Proportion of health facilities with no stock-out of essential drugs in the last three months Baseline: TBD Target: 80% | MOHSW Annual Report HMIS and National Blood Safety Report HMIS and National Blood Safety Report HMIS and EPHS accreditation report, HMIS National Budget, MOH&SW Financial Report HMIS, NDS Report |  |  |  |
| Output 3.1.4 Enhanced technical capacity of health workers and community volunteers for increased coverage of case management of common childhood illness at community level | Proportion of communities with at least one Trained Community Volunteer Baseline: TBD Target: 80% Proportion of diarrhea cases among children under five effectively treated with ORT Baseline: 72.1% Target: 80% Proportion of ARI cases among children under five treated with effective antibiotics Baseline: 48.7% Target: 75% Proportion of malaria cases in children treated with ACT within 24 hours of onset of fever Baseline: 37.6% Target: 80% | MOH&SW Report HMIS and DHS HMIS and DHS HMIS, MIS |  |  |  |
| Output 3.1.5 National capacity enhanced to maintain immunization coverage over 90% in all counties. | Number of counties with Polio-free status maintained and non-Polio AFP rates of <2/100,000 population less than 15 years of age Baseline: Polio: 15 Counties AFP: 13 Counties Target: Polio: 15 Counties AFP: 15 Counties Proportion of health facilities conducting immunization outreach through the RED strategy. Baseline: TBD Target: 90% Proportion of health facilities with functioning cold chain system Baseline: 71% Target: 90% Proportion of health facilities with no stock-out of vaccines and related supplies in the last three months Baseline: 60% Target: 90% | MOH&SW EPI Report HMIS HMIS MOH&SW CI Report and HMIS |  |  |  |
| Output 3.1.6 Enhanced capacity of health workers and community volunteers to deliver essential nutrition interventions with decentralized service delivery at community level | Coverage of bi-annual Vitamin A supplementation of children age 6-59 months. Baseline: 86% Target: 95% Proportion of pregnant women receiving iron supplements Baseline: 41% Target: 70% Proportion of children under 5 years treated for moderate and severe acute malnutrition Baseline: TBD Target: 80% | HMIS and DHS HMIS and DHS Nutrition/SMART survey |  |  |  |
| Outcome 3.2 Education School-aged girls and boys and youth have increased access to quality inclusive ECD, Basic, Post-Basic and Alternative basic Education, especially in counties with education indicators below the national average. | Gross Enrolment Rate, (ECD, BE) B: 106; T: 110 Gross Completion Rate (ECD, BE) B: 83; T: 90 % of girls transiting from Basic to Post Basic Education B: TBD; T: 20% increase yearly % of enrolled students completed PE and ABE with acceptable learning achievements (By Grade 1, 3, 6, 9 & 12) B: TBD; 20% increase yearly *all data - for ALL indicators (ECD, BE, ABE, PBE) will be disaggregated by sex and district, with assessment of inclusion of those with disabilities | School Census/EMIS School Census/EMIS School Census/EMIS Specific studies | Assumptions Gov. committed to adequate long term funding including funding for complementary support schemes Strong coordination within education sector and relevant ministries MOE committed to implement Education Act in line with PRSP goals. Risks Weak infrastructure and governance system in education Utilization of quality education service remains low due to household factors, such as poverty, or competition from traditional bush schools, which are not sufficiently addressed by other UNDAF programs Limited coverage of current programme of teacher training |  |  |
| Output 3.2.1 A holistic ECD approach designed, modelled and piloted | Existence of approved ECD Curriculum. Baseline: Not approved Target: Approved % of ECD teachers trained on the new curriculum Baseline: 0% Target: 60% of these under trained teacher in at least 7 low-performing counties Proportion of public schools received ECD materials Baseline: None Target: All public schools offering ECD have appropriate materials Proportion of schools in low performing counties conducting performance assessment according to standards. Baseline: 0 Target: 30% Percentage of public schools implementing ECD according to Child Friendly School (CFS) standards Baseline: 0 Target : 20% | MoE Report Training report Project Monitoring report Commissioned survey Project Monitoring report |  |  |  |
| Output 3.2.2 Children learning level in Basic Education improved | Competency-based Basic Education Curriculum revised Baseline: Curriculum exists and being piloted Target: 80% public schools using revised curriculum with 50% of their teachers trained Student to Textbook ratio for grades 5-9 in core subjects Baseline: 2009 student/textbook ratio: 4:1 overall Target: Student to textbook ratio no more than 2:1 for grades 5-9 in core subjects Proportion of children at risk of dropping out who receive long-term complementary support. Baseline: TBD in 2012 Target: 20% Percentage of schools meeting standards of learning achievement for grade 1,3,6,9 Baseline: TBD Target: 70% Code of Conduct for security of children in place Baseline: No code of conduct Target: Code of Conduct approved | EMIS School Census EMIS school census EMIS, MoE/Education Pooled Fund Progress report EMIS, MoE/Education Pooled Fund Progress report MoE |  | UN Women and UNMIL to provide policy support on girls education and human rights |  |
| Output 3.2.3. Education management system strengthened including the decentralization process | Number of Centers of Excellence established Baseline: 0 Target: 3 Centers of Excellence set up; Percentage of newly constructed or rehabilitated schools meeting the specified standards Baseline: TBD Target: 80% Existence of guidelines to improve learning materials utilization. Baseline: No guidelines Target: Guidelines utilized Number of county school boards functioning Baseline: TBD in 2012 Target: All 15 counties | Reports from MOE Audit reports Validated through commissioned study DEO/CEO Inspection reports to M&E Unit; |  |  |  |
| Output 3.2.4 Expanded Post-Basic Education provision strengthened | Number of students placed under safe supervised single-sex residential accommodation that is regulated by social welfare services Baseline: TBD in 2012 Target: 4,000 girls and 2,000 boys New model schools for ECD/BE/ABE located in areas over 5 miles from existing schools Baseline: TBD in 2012 Target: 5,000 children living over 5 miles from any Grade 4 and above school now within 5 miles of a school Existence of higher education strategic plan Baseline: No higher education strategic plan Target: Higher Education Strategic Plan developed Number of students participating in pilot Innovative Education. Baseline: None Target: 500 students, including at least 300 girls, participating in pilot in 5 selected areas Number of primary and secondary schools implementing the integrated sexuality education curriculum. Baseline: 2,000 Target: 2,627 | EMIS School Census School mapping and census National Commission of Higher Education Pilot project reports |  |  |  |
| Output 3.2.5 Alternative Basic Education (ABE), for out-of-school children and youth, designed and implemented | Percentage of public schools implementing Ability-based ABE curriculum, including life-skills; Baseline: TBD Target: 80% Percentage of grade 3 and 6 students meet the Competency based assessment of literacy, numeracy and life-skills. Baseline: TBD Target: 70% Percentage of ABE learners who continue to junior secondary Baseline: N/A Target: 10% Percentage of out of school children receiving long-term complementary support, including scholarship grant system Baseline: TBD in 2012 Target: 20% | EMIS School Census EMIS with commissioned study MoE/Education Pooled Fund progress report |  | UN Women and UNMIL to provide policy support on girls education and human rights |  |
| Output 3.2.6 Increased government ownership and implementation of effective school feeding programme in low performing areas | Number of girls and boys receiving UN’s food assistance. Baseline: 320,000 boys and girls for hot meals and 9,000 girls in grade 4-6 receiving Girls Take Home rations. Target: 234,000 boys and girls for hot meals and 6,000 girls in grade 4-6 Girls Take Home rations. Number of school benefiting from the full essential learning package Baseline: TBD in 2012 Target: 200 Number education unit at central and county level with capacity to design and implement school feeding nutrition programme. Baseline: Target: 8 Existence of National School Feeding programme policy and National Home Grown School Feeding Programme strategy Baseline: Target: National School Feeding Policy adopted Home Grown School Feeding Strategy developed | EMIS; School Census MOE/WFP monitoring EMIS; School Census; MOE School Feeding Report MOE School Feeding Report |  |  |  |
| Outcome 3.3 Social Welfare Social welfare systems and services are improved and utilized, especially by the most vulnerable groups and individuals. | Percentage of health budget allocated for social welfare Baseline: Target: 10% increase over baseline each year Birth registration coverage among children under 5 years. Baseline: 7% (BVS Data 2012) Target: 50% nationwide % of referred social welfare cases processed through a national case management system Baseline: 0 Target: 75% of cases | National budget LDHS, BVS birth registration data MoHSW service provision data | Assumptions Sustained financial and human resource investment made by Government of Liberia for social service delivery Coordination amongst service delivery agencies and institutions is operational at both the national and sub-national levels Risks Community norms and attitudes impede effective case reporting and response | Major partners for all interventions include MOHSW (including the Department of Social Welfare and Bureau of Vital Statistics) and MOGD as primary coordinating and implementing agencies. Additional coordination work will take place with various rule of law institutions including the WACPS of LNP |  |
| Output 3.3.1 The capacity of relevant actors to manage social welfare cases, monitor residential facilities, and promote family-based care is improved | Existence of social welfare case management system with links to government institutions Baseline: No case management system exists Target: Case management system exists Proportion of districts with at least one trained social worker Baseline: 24% (16/68 districts) Target: 75% Proportion of districts with persons trained to deliver psychosocial support Baseline: TBD (in 2012) Target: 80% Proportion of children living in institutions whose status is reviewed at least once every year Baseline: TBD Target: 100% Existence of a foster-care system and regulatory structure Baseline: No foster care system exists Target: Foster care system and regulatory structure are operational | MoHSW service provision data MoHSW staff data MoHSW staff data MOHSW service provision data MOHSW service provision data |  |  |  |
| Output 3.3.2 Birth registration services available across the country | Proportion of districts with birth registration services Baseline: 50% (34/68 districts) Target: 75% of districts Proportion of registered births for which certificates are issued within 30 days Baseline: TBD Target: 75% | BVS birth registration data BVS birth registration data |  |  |  |
| Output 3.3.3 A safe and secure environment for survivors and individuals at risk of violence, HTP, exploitation, discrimination, abuse and neglect exists across the country | Proportion of Districts with a community-based protection and violence prevention structure Baseline: TBD in 2012 Target: 50% Number of counties with a one-stop service delivery center for survivors of VEDAN and HTP Baseline: 0 Target: 6 Number of government-operated safe homes operating in compliance with established standards Baseline: 0 Target: 5 | MoGD service point data UNJP on GBV service provision data UNJP on GBV service provision data |  |  |  |
| Outcome 3.4 Social Protection Vulnerable households and groups benefit from appropriate social protection services and systems. | Percentage of food-insecure population in targeted areas Baseline: 41% Target: 30% Essential asset deficiencies among households in targeted areas Baseline: TBD, based on CWIQ 2010 Target: TBD, based on CWIQ 2010 | CFSNS Report CWIQ Report | Assumptions Targeting mechanisms in social protection programs effectively identify and include most vulnerable households and individuals Transfer recipients distribute and utilize transfers appropriately GoL decision-making on social protection intervention areas remains need-based and depoliticized. Risks Systemic shock or emergency dramatically increases size of vulnerable population |  |  |
| Output 3.4.1 Government of Liberia capacity to coordinate and deliver social protection services is enhanced | Existence of National Social Protection Policy Baseline: No policy exists Target: National policy exists Functioning inter-ministerial planning mechanisms Baseline: No inter-agency planning mechanisms in place Target: Functional inter-ministerial mechanisms in place Existence of national social protection monitoring and evaluation system Baseline: No coordinated M&E system exists Target: National M&E system for social protection exists National Child Well-Being Council functioning in line with the Children’s Law Baseline: Children’s Law passed, Council not established Target: Council established and functioning | Existence of cabinet-approved policy Inter-ministerial coordination arrangements National social protection M&E system Appointment and approval of Council members and regular meetings |  | Key partners in social protection interventions will include MOPEA/MOF for inter-ministerial coordination, MOGD, MOHSW, MOL, MOA, LACE and others for implementation and coordination |  |
| Output 3.4.2 Vulnerable populations, especially youth, are better prepared for work and have increased opportunities for transitional income generation. | Number of youth, women and farmers trained in employment and livelihood skills programs Baseline: WFP:100 ; WB: TBD; ILO: TBD Target: TBD Number of individuals participating in labour intensive social work schemes either in infrastructure or other labour-intensive schemes targeting vulnerable especially youth and women Baseline: WFP: 7,500, WB: TBD, ILO: TBD Target (annual): WFP: 10,000; WB: 15,000; ILO: TBD | WFP, ILO and WB programme data WFP, ILO and WB programme data |  |  |  |
| Output 3.4.3 The most vulnerable households and individuals receive appropriate safety net transfers. | Number of vulnerable households and individuals receiving food assistance (FFW/CFW activities) in food insecure areas Baseline: 12,500 beneficiaries under CFW and 25,000 beneficiaries for FFW Target: Annual Target: Food For Work- 20,000 beneficiaries and Cash For Work- 30,000 beneficiaries Number of labor-unavailable households in targeted areas receiving cash transfers Baseline: 1,900 households Target: 10,000 households | GoL and UN social protection service provision data MOGD SCT Secretariat data |  |  |  |
| Outcome 3.5 Water, Sanitation & Hygiene Population has increased utilization of safe water and practice safe sanitation and hygiene in underserved areas | % of population utilizing sustainable improved water facilities Baseline: 68% Target: 77% % of population utilizing sustainable improved sanitation facilities Baseline: 17% Target: 40% % of population washing hands with soap at 3 critical moments Baseline: TBD Target: 20 points increase Approved WASH advocacy plan exist Baseline: No Target: Yes | LDHS, WHO/UNICEF JMP LDHS, WHO/UNICEF JMP LDHS, WHO/UNICEF JMP Sector report, (mid- term, 5 years), CSO report | Assumptions The water atlas is updated and remains the main sector prioritization tool Adequate financial resources are allocated to the sector by Government and donors Government of Liberia remains committed to implement adopted sector policies and strategic plan Risks Inadequate capacity of County and district level to plan, implement and monitor WASH services. | Ministry of Public Works, Ministry of Lands, Mines and Energy, Minstry of Health and Social Welfare, Liberia Water and Sewer Corporation, NGOs, USAID |  |
| Output 3.5.1 400,000 additional persons have improved water and sanitation services, and knowledge of safe hygiene practices, in underserved areas | Number of persons with access to improved water facilities Baseline: 0 Target: 400,000 additional persons Number of persons with access to improved sanitation facilities Baseline: 0 Target: 400,000 additional persons Standard hygiene promotion guidelines developed and disseminated Baseline: N Target: Y Number of municipalities with functional solid waste management system Baseline: TBD Target: WB | Periodic reports, sector review report Periodic reports, sector review report Project report Periodic reports, sector review report |  | Ministry of Public Works, LWSC, NGOs, USAID |  |
| Output 3.5.2 500 primary schools and 50 Health facilities have implemented WASH package in underserved areas | Number of schools benefitting from WASH in School (WinS) package. Baseline: 0 Target: 500 Number of health facilities benefitting from WASH package Baseline: 0 Target:50 clinics/health facilities | Project reports, Annual reviews Project reports, Annual reviews |  | Ministry of Education, Ministry of Health and SW, NGOs |  |
| Output 3.5.3 WASH governing bodies established | Existence of NWRSB, WSSC, RWSSB and DCMHYP (Y/N) | Executive orders or Acts |  | MPW, MLME, MOHSW, LWSC, USAID |  |
| Output 3.5.4 Effective WASH sector M&E capacity is strengthened at central and County levels | Existence of sustainable M&E system Baseline: NO Target: Yes | Periodic M&E reports available |  | MPW, MLME, MOHSW, LWSC, USAID |  |
| Output 3.5.5 Financial management capacity in WASH sector is strengthened at central level | Existence of Annual financial review mechanism. Baseline: No Target: Yes | Annual sector reports |  | MPW, MLME, MOHSW, LWSC, USAID |  |
| Outcome 3.6 HIV-AIDS Scaled up access to and utilization of HIV Prevention, treatment, care and support services. | Percentage of HIV positive women who receive ARVs to reduce the risk of Mother to child HIV transmission Baseline: 54.2% Target: 85% Percentage of infants born to HIV positive women receiving virological test within 2 months Baseline: 20% Target: 85% Percentage women and men aged 15 to 49 who received an HIV test in the past 1 year Baseline: 19% Target: 85% Percentage of MSM reached with HIV prevention programmes Baseline: 15% Target: 65% Number of HIV and AIDS Workplace policies and programs implemented in targeted sectors Baseline: 1 Target: 1 | ANC registers, DHS UNGASS ANC registers NACP M&E programe data (2008-2011) Spectrum Projection (EPP) 2011 MOT MOT Workplace Policies documents | Assumptions The multi-sector response to HIV and AIDS is well coordinated. Risks Inadequate national commitment or international coordination to sustain the HIV and AIDS response | UNFPA, WHO, UNICEF, MoHSW for PMTCT providing funding and technical assistance for PMTCT in public and private health facilities UNDP & UNAIDS, NAC, MOHSW, MOJ for MSM providing funding and programming assistance for reaching MSM and other key populations ILO and MoL | PMTCT us$1,600,000 (us$300,00O per year) US$250,0000 (US$50,000/year) US$250,000 (US$50,000/year) |
| Output 3.6.1 Increased knowledge and understanding of the causes of HIV infection and measures of prevention among youth and adolescents. | Percentage of young women and men aged 15–24 who correctly identify ways of preventing HIV and rejecting major misconceptions about HIV transmission Baseline: 23.5% Target: 70% Proportion of youth and adolescents tested for HIV and receiving their results disaggregated by age Baseline; NA Target: 30% Existence of comprehensive HIV and Nutrition Guidelines (Y/N) | LDHS MARPs, BioBSS | The next DHS will include HIV to ensure consistence of data. | LISGIS, unfpa, unicef | US$2,000,000 |
| Output 3.6.2 Increased number of women accessing ARVs/ART services | Percentage of women aged 15 – 49 testing for HIV and receiving their results (PMTCT setting) Baseline; 96% Target: 100% Percentage of mothers receiving perinatal ART or prophylaxis Baseline; 21% Target: 80% Percentage of infants born to HIV positive women receiving virological test within 2 months Baseline; 65% Target: 100% | NACP Quarterly reports HMIS UNGASSS EID records | Resources especially from the GF will continue to be available | UNICEF, WHO, MoHSW | Included in PMTCT |
| Output 3.6.3 Increase in HIV-AIDS positive persons accessing quality HIV care, treatment and support services | % of estimated HIV positive incident TB cases that receive treatment for TB & HIV Baseline; 50% Target: 90% Percentage of adults and children with HIV known to be on treatment for 12 months after initiation of ART Baseline: 62% Target: 85% Number of health facilities providing ART services Baseline; 29 Target: 320 | HMIS,TB Incident Study, NACP, NTLCP Cohort study UNGASS report | Resources especially from the GF will continue to be available Government will fund the HIV response in particular HIV treatment with its domestic resources | WHO, MoHSW, NACP, NAC | US$2,500,000 (us$500,000) |
| Output 3.6.4 NAC capacity strengthened to implement multi-sectorial and decentralized National HIV Response | Existence of National Commitments and Policy Instruments (NCPI) (Y/N) |  | Government will continue to consider HIV as a key development priority |  | US$1,500,000 (US$300,000/year) |

| UNDAF Priority 4: Inclusive Governance and Public Institutions |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| National Development Goal: to build and operate efficient and effective institutions and systems, in partnership with the citizens, that will promote and uphold democratic governance, accountability, justice for all and that will strengthen peace. |  |  |  |  |  |  |  |  |  |
| Outcomes/Outputs |  | Indicators, Baselines, Targets | Means of Verification |  |  | Risks and Assumptions |  | Role of Partners | Indicative Resources |
| Outcome 4.1: Modernization of the Legislature: By 2017 Liberia has political institutions equipped with inclusive systems and mechanisms for legislative, representational and oversight functions that facilitates deepening of democracy. |  | Indicators: Revised and improved version of rules and procedures for the Legislature codified and published; (Y/N) Baselines: rules and procedures do not facilitate effective functions of the legislature Target: Revised rules and procedures for both houses published Indicator: Women’s membership and chairs in House Committees. Baseline: most of the House committees have below 15% women’s representation. Target: at least 30% women represent in all committees and women chair 30% of committees; women legislative caucus is effectively engaged and integrating a gender perspective into bills. Indicator: Revised and improved operational mechanisms and SOPs of the National Elections Commission Baseline: Administrative and operational procedures and guidelines are unclear. Target: Published revised SOPs | Amended rules of procedures published for both Chambers of the Legislature House and Senate committee composition SoPs |  |  | Assumptions Political will of the Legislature continues to exist. Reduced number of Executive sessions. Legislators actively engaging and accountable to constituencies. Oversight is carried out in the public’s interest. Capacity of the Legislative Secretariats fully supported. Separation of legislative and executive functions fully observed Risks Conflict of public and private interests in legislation Inadequate clarity of the role and appreciation of the constitutional responsibilities of Legislature in democratic governance Weak adherence to the rule of law. |  |  |  |
| Output 4.1.1: By 2017, the Legislature is better able to perform legislative, representational and oversight functions in an inclusive, effective and efficient manner |  | Indicator: Mechanisms for inclusive constituency engagement Baseline: sporadic and infrequent constituency engagement which are not issue-based and do not ensure reflection of views and concerns of broad spectrum of constituency; Target: planned periodic and issue-based constituency engagement, all inclusive and ensures feedback mechanism Indicator: demonstrated ability of Legislators to initiate, introduce, review and sponsor bills in a timely and inclusive manner; Baseline: limited ability to initiate, articulate issues (particularly legal drafting), review bills, ; Target: enhanced capacity of Legislators, legal drafting department and committee support office to provide support for drafting and presenting evidence-based bills; public hearing made mandatory. Indicator: No of reports including of audits received, reviewed and responded to on time; Baseline: TBE Target: X all reports, including audit are reviewed and substantive responsive provided in a timely manner | Legislators’ Hand Book New Bills; time from initiation to completion of bills; conte4nts of bills, policy briefs, research. Daily Journals for each sitting and annual Legislative Journal for Each Chamber of the Legislature |  |  |  |  |  |  |
| Output 4.1.2 By 2017, the NEC has the capacity to independently conduct free, fair, transparent and credible elections |  | Indicators: Electoral law reviewed and amended and published and proposals made for constitutional amendment; Baselines: gaps and deficiencies in the existing electoral framework; Target: Proposals for constitutional amendment made.e. Indicator: public confidence in the competence, impartiality and independence of NEC. (Y/N) Indicator: systems, rules, procedures relevant to institutional and administrative functions reviewed and published; Baseline: GAC report reveals weak administrative and institutional systems and mechanisms (human resources, finance, asset management and procurement in particular); Target: Clear SOPs developed; staff oriented and fully rolled out. Indicator: NEC’s staff have relevant skills and knowledge to conduct elections at national and local level in an inclusive, participative and transparent manner, Baseline: 2011 national elections were conducted with technical support from its international partners; minimum infrastructure and procedural guidelines and mechanisms are in place. Target: NEC is fully capable, technically and operationally, to organise and conduct elections. Indicators: mechanisms for engagement of political parties, CSOs, women’s groups, youth, and media are well defined and strengthened. Baseline: weak capacity of NEC’s external relations division to engage stakeholders in a sustained and meaningful manner. Target: NEC’s external relations division is robust in its planning, operations and public outreach; the division is fully equipped in terms of staff skills and capacity and fully engaged with stakeholders particularly IPCC, media, women and youth groups, local authorities. | Amended electoral law presented to the Legislature. Media reporting, international observers’ review. NEC’s operational and logistical plans; NEC’s divisions/ units’ delivery/reports; Media reporting; Published new law Proposals for constitutional amendment |  |  | Assumptions Sections within the NEC are depoliticized and strengthened, particularly the Legal Section. Risks Political parties continue to reject the NEC as a partisan body. Amending the electoral law is politicized. |  |  |  |
| Output 4.1.3 By 2015, organized groups of Women, Youth, media and CSOs capacity to engage in political processes particularly in electoral and legislating processesenhanced; |  | Indicator: Roles and regulatory framework for CSOs clarified/established Baseline: Women’s/Youth/Media (WONGOSOL, FLY) have structure and secretariats ; Media has a regulatory framework; Target: An overall regulatory framework for CSOs developed/published. Indicator: Women, Youth, media and CSOs received trainings on the use of framework, advocacy, lobbying and Civic Rights/Human Rights, Participation and Engagement; Baseline: TBE Targets: Women, Youth, media and CSOs are fully engaged in political processes | Corresponding laws and statutes Engagement and contributions of Women, Youth, media and CSOs |  |  |  |  |  |  |
| Outcome 4.2 Constitutional and Legal Reform: By 2017, a comprehensive review of the Constitution is completed with a balanced relationship between the three arms of government and a framework that guarantees democratic governance and equal rights of all citizens. |  | Indicator: Review completed, proposals made (Y/N) Indicator: Constitution guarantees equality of all citizens (male and female) in terms of social, political and economic rights (Y/N) Indicator: Number of international/regional HR instruments domesticated, implemented and reported on by 2017 Baseline: Currently reports on XXX Target: Implementation of all relevant instruments are being reported on a regular basis. | proposals Relevant constitutional provisions Laws, statues and periodical reports |  |  | Assumptions Political will to reform is maintained at the highest level Broad-based consultation held on reforms Risks Lack of effective communication ability to engage public at large on constitutional and legal issues at all levels Deliberate move to capture reform process by vested interest |  |  |  |
| Output 4.2.1 By 2014, review of current constitution and legal framework undertaken and new proposals drafted |  | Indicator: New proposals consistent with international human rights standards and balanced relationship between three arms of government in place (Y/N) Indicator: New constitution and legal provisions guaranteeing equal rights of women and men of all ethnic/religious backgrounds. (Y/N) | Proposal and its provisions Relevant provisions of the Constitution |  |  |  |  |  |  |
| Output 4.2.2 By 2017, all Human Rights instruments and international treaties to which Liberia is a state party are domesticated in line with the constitutional provisions |  | Indicator: Liberian legal instruments are fully consistent with international standards of human rights set forth in all conventions and treaties to which Liberia is a State Party (Y/N) Indicator: Liberia reports periodically on human rights conventions and treaties as per the accepted international practices (Y/N) | Relevant laws and statutes (their provisions) Periodical reports |  |  |  |  |  |  |
| UNDAF Priority 4: Inclusive Governance and Public Institutions |  |  |  |  |  |  |  |  |  |
| National Development Goal: to build and operate efficient and effective institutions and systems, in partnership with the citizens, that will promote and uphold democratic governance, accountability, justice for all and that will strengthen peace. |  |  |  |  |  |  |  |  |  |
| Outcomes/Outputs | Indicators, Baselines, Targets |  |  | Means of Verification | Risks and Assumptions |  | Role of Partners |  | Indicative Resources |
| Outcome 4.3 Natural Resources Management: By 2017, Liberia has an effective and efficient natural resource management framework enabling transparent, accountable and equitable distribution of economic benefits and protection of rights of all. | A regulatory framework for natural resources management with community participation endorsed (with provision for oil, mines, fisheries, forest, land, etc.); (Y/N) Government capacity for contracts, agreements and concessions negotiations supported by expert knowledge, skills, facts and data (Y/N) Land reform policy developed with provision for protection of rights of all concerned, with women’s rights to land ensured in law and practice (Y/N) Complaint and redress mechanisms exist and in use (Y/N) Existence of transparency and accountability mechanisms in project distribution and resource expenditure of social and economic benefits (Y/N) Community-based groups and civil society organizations engaged in advocacy and budget monitoring with a human rights-based approach (disaggregated per sector, fund, county, district) |  |  | Legal Framework and its provisions Contents and terms and conditions of contracts, agreements, concessions; Legislations on land reform and the provisions of citizen’s rights Institutional arrangement, structure, rules and procedures and staff | Assumptions Leadership and political will is maintained at the highest levels Community is brought fully on board Negotiation process fully transparent Social benefit-costs are fully accounted for Principles of inter-generational sharing of resources fully observed Risks Short-term gains undermine longer-term social an economic costs Varied understanding of stakeholders Ethical standards, may be compromised; Corruption is not sufficiently addressed |  |  |  |  |
| Output 4.3.1 By 2015, an expanded, comprehensive regulatory framework for natural resources management formulated and endorsed | Land policy drafted and published (Y/N) LEITI’s capacity and mandate expanded (Y/N)Information management system established and functional (Y/N) Community groups and CSOs fully engaged in concession monitoring (Y/N) |  |  | New land policy Revised/approved mandate, staff (number and functions) MIS and the associated institutional arrangements (people, equipment, tools) |  |  |  |  |  |
| Output 4.3.2 By 2016, complaint and redress mechanism for natural resources management are established and operational | Alternative (land) dispute resolution (ADR) mechanism established, tested and rolled-out (Y/N) Community-based monitoring fully integrated into M&E system with a human rights-based approach (Y/N) |  |  | Institutional arrangements (rules, procedures, structures) and supporting instruments |  |  |  |  |  |
| Output 4.3.3 By 2016, a robust M&E framework developed and adopted | M&E system, mechanisms, and plans in place, and annual reports published (Y/N) |  |  | M&E System, Monitoring Reports, Electronic Database |  |  |  |  |  |
| Output 4.3.4 By 2015, government’s capacity for contracts, agreements and concessions negotiations enhanced | Electronic database on contracts, agreements and concessions maintained, in use and publicly accessible. With information on the percentage contribution of the sector to national revenue (Y/N) Staff of relevant institutions have successfully undertaken technical trainings in appropriate tools. (Y/N) |  |  | Database and the extent of its accessibility Training reports |  |  |  |  |  |
| Outcome 4.4 Public Sector Institutions and Civil Service Reform By 2017, Liberia has an improved and decentralized public sector and civil service providing fair and accountable basic services to peo.le | Public sector reformed and functions streamlined and rationalized Number of national ministries/agencies implementing decentralization consistent with the National Decentralization Policy Baseline - Nil Target: all service sector ministries and relevant oversight entities; 15 counties share revenue with national government and also collect local revenue for development administration and management Participation o of citizens, in particular women, youth and CSOs in county and local planning, budgeting, and decision making processes institutionalized (Y/N) National Disaster Risk Management policy effected with key sector ministry/agency plans, and capacity assessed and operational at national and county level. (Y/N) |  |  | Published MFR and Annual reports Annual reports, Progress report on decentralization implementation; Physical presence of institutions; Annual budgets Presence of salutatory bodies at local level and share of CSOs representation New policy and institutional arrangements | Assumptions Leadership and political will remain strong Civil Service works through a performance-linked compensation system National and local institutions are economically viable Risks Delivery of public goods and services affected due to lack adequate infrastructure and amenities |  |  |  |  |
| Output 4.4.1 By 2015, county governments have operational and technical capacity to formulate and implement county development plan and budget. | Number of ministries and agencies that decentralized functions to counties and districts as per the national implementation plan Baseline: Nil Target: all service sector ministries and relevant oversight entities 15 county governments have formulated annual development plan and budgets and implementation commenced. |  |  | Physical presence of entities, staff, annual reports Annual county development plan and budgets |  |  |  |  |  |
| Output 4.4.2 By 2016,public sector institutions’ capacity is enhanced with clearly defined mandates, structures and functions | Mandates and functions of public sectors institutions reviewed/published (Y/N) Pay and pension reformed, job classified and incentives harmonized for national and local government staff (Y/N) |  |  | New MRF Standardized Payroll, job classification. |  |  |  |  |  |
| Output 4.4.3 By 2016,county service delivery and out -reach are informed by needs and priorities of citizens | County and district planning councils institutionalized and fully functional with adequate representation of women, youth and CSOs Biennial public perception survey on quality and accessibility of service delivery conducted, reports accessible to wider public at national and community level (Y/N) Information on public affairs including budgetary allocation and utilization of public resources publicized at county, district and facility level (Y/N) % of representation of women, youth and CSOs in community level committees (peace building, health, education, WASH, child welfare, etc.); Baseline: Standard Baseline to be determined Target: at least 50% women, 25 % youth |  |  | County and district planning manuals ; Count council proceedings Survey reports, public accessibility Public Notice Board, media broadcasts; public knowledge of (access to) relevant information |  |  |  |  |  |
| Output 4.4.4 By 2016, National Disaster Risk Reduction (DRR) policy implemented and supported by a commission with clearly defined mandates | National DRR policy is translated in to national priorities (Y/N) |  |  | Sectoral implementation plans and reports |  |  |  |  |  |
| Output 4.4.5 By 2015,effective Public Finance Management (PFM) with a transparency and accountability mechanism is instituted | National and Local Government Budgeting exercises (Y/N) |  |  | National/local budgets, audit reports |  |  |  |  |  |

At the time of the UNDAF preparation, the World Bank is uncertain of its programme structure and funding beyond the end of 2012.  Their important participation in the UNDAF will be reflected in a revised UNDAF Action Plan following its first Annual Review in 2013.

Peaceworks “Looking for Justice: Liberian Experiences with and Perceptions of Local Justice Options”, 2009, Unites States Institute of Peace. Total number of civilian cases- 3181, criminal cases – 1871, p. 75.No data disaggregation available for this source