Afghanistan

Avian Influenza Control and Human Pandemic Preparedness and Response Project

Environmental Management Plan

Prepared by: The Islamic Government of Afghanistan (GOA):

Ministry of Agriculture, Irrigation and Livestock (MAIL) and Ministry of Public Health (MOPH)

(July 27, 2007)

Executive Summary

The Islamic Republic of Afghanistan is embarking upon the Avian Influenza Control and Human Pandemic Preparedness and Response Project.  The project is funded by the World Bank (WB).  In line with the national legislative requirement and WB’s safeguard policies, an environmental management plan (EMP) of the AI project has been developed.  This document presents this EMP.

Background

Since 2003, highly pathogenic avian influenza (HPAI) caused by the H5N1 subtype has been spreading at an alarming rate, from East Asia to Central Asia, and now to the Middle East, Europe, Africa, and South Asia.  In addition to its impact on animal health, with millions of domestic poultry having died or been destroyed worldwide, H5N1 has been causing severe human disease.

Afghanistan has some of the poorest social, economic and health indicators in the world with high susceptibility to communicable diseases.  Inadequate facilities and capacities to detect, control, contain and mitigate an outbreak of communicable disease have made this country highly vulnerable to diseases such as avian influenza.

In March 2006, an inter-sectoral Task Force prepared the Afghanistan National Avian Influenza and Influenza Pandemic Preparedness and Response Plan (ANIPPRP).  Subsequently, the Government of Afghanistan requested the World Bank to finance the Plan.  The ANIPPRP was later supplemented with an Operational Plan, which formed the basis for the World Bank appraisal for the present project.

The Project

The overall objective of the Project is to minimize the threat posed by HPAI to humans in Afghanistan by controlling such infections among birds, especially domestic poultry, and preparing for, controlling, and responding to possible human infections, especially an influenza epidemic and related emergencies.  This objective will be achieved through three types of interventions: (i) prevention; (ii) preparedness and planning; and (iii) response and containment.

The project will finance activities under four components: Animal Health; Human Health, Communications and Public Awareness; and Institutional Coordination and Project Management.

The Animal Health component will support a national program to develop and implement HPAI prevention, containment, control, and eradication activities in the livestock sector of Afghanistan creating an effective system for improved bird health surveillance, diagnostic analysis and disease control in accordance with FAO/OIE standards.

The Human Health component will support a national program of activities to prevent, detect, respond to and mitigate the impact of human illness caused by avian or pandemic influenza.  Component activities will involve emergency and long-term developments to address priority gaps in disease surveillance, control and treatment.  It would also contribute to MOPH’s ongoing program for re-establishing public health capacity that was destroyed during decades of conflict.

Under the coordination of the communications specialist based at the AI Secretariat, and with the advise and technical assistance of the Communications Task-Team (including donors, and NGOs), the communications component will finance baseline research, design, test and implementation of a comprehensive and integrated communications strategy.

The last component will support the institutional coordination and management of the Project.

Environmental Management Plan

The present EMP has been developed in response to the regulatory requirements in the country, defined by the recently promulgated environmental protection act, as well as the WB Operational Policies.

The overall objective of the EMP is to improve the environmental performance of the project, and to ensure that the proposed activities do not cause an unacceptable level of environmental impacts or public health risks.

The EMP reviews the national regulatory and WB’s safeguard policies relevant to the project.  It identifies and assesses the potential environmental impacts and public health risks that may be caused by the project, and also recommends mitigation and monitoring measures to reduce if not completely eliminate these impacts.  The document also determines the training and capacity building needs with regard to the environmental management of the project.  In addition, the EMP defines the implementation mechanism, and assigns roles and responsibilities, for the mitigation measures, monitoring requirements and environmental trainings during the project execution.  Finally, the EMP specifies the communication and documentation protocol for the environmental management of the project.

The present EMP has been developed in a consultative and participative manner, thus making it relevant to the local conditions and existing capacities within the implementing ministries.  If adequately implemented, this Plan will not only enhance the environmental performance of the project, but will also help in mainstreaming the environmental management within the implementing ministries.

Acronyms

| ADB | Asian Development Bank |
| --- | --- |
| AH | Animal health |
| AHID | Animal and human influenza disease |
| AI | Avian influenza |
| AIRP | Avian Influenza Response Project |
| APHI | Afghanistan Public Health Institute |
| ANIPPRP | National Avian Influenza and Influenza Pandemic Preparedness and Response Plan |
| AVA | Afghan Veterinary Association |
| CCU | Command and Control Unit |
| CDC | Center for Disease Control |
| DEWS | Disease Early Warning System |
| DFID | Department for International Development |
| EA | Environmental Assessment |
| EFP | Environmental Focal Point |
| EIA | Environmental Impact Assessment |
| EMP | Environmental Management Plan |
| ERT | Emergency Response Team |
| EU | European Union |
| EWMS | Environmental and Waste Management Specialist |
| FAO | Food and Agriculture Organization |
| FIDIC | International Federation of Consulting Engineers |
| GDPP | General Department for Policy and Planning |
| GoA | Government of Afghanistan |
| GPAI | Global Program for Avian Influenza |
| GPS | Global positioning system |
| HH | Human health |
| HLP | Horticulture and Livestock Project |
| HPAI | Highly pathogenic avian influenza |
| IST | Implementation Support Team |
| MAIL | Ministry of Agriculture, Irrigation and Livestock |
| MOC | Ministry of Commerce |
| MOF | Ministry of Finance |
| MOI | Ministry of Interior |
| MOPH | Ministry of Public Health |
| MORRD | Ministry of Rural Rehabilitation and Development |
| M&E | Monitoring and evaluation |
| NAIC | National Avian Influenza Committee |
| NAIS | National Avian Influenza Secretariat |
| NEPA | National Environmental Protection Agency |
| NERC | National Emergency Response Committee |
| OIE | World Organization for Animal Health / International Office of Epizootics |
| OP | Operational Policy |
| OSHA | Occupational Safety and Health Administration |
| PAIC | Provincial Avian Influenza Committee |
| POM | Project Operational Manual |
| PPD | Planning and Policy Department |
| PPE | Personal protective equipment |
| SVD | State Veterinary Department |
| ToR | Terms of reference |
| ToT | Training of trainers |
| UNEP | United Nations Environment Program |
| UNICEF | UN International Children and Education Fund |
| USAID | United States Agency for International Development |
| USDA | United States Department of Agriculture |
| VFU | Veterinary Field Units |
| WB | World Bank |
| WHO | World Health Organization |

Contents

Executive Summary	ii

Acronyms	iv

1	Introduction	1-1

1.1	Background	1-1

1.2	Project Operational Manual	1-2

1.3	EMP Objectives	1-2

1.4	Methodology	1-3

1.5	EMP Components	1-3

2	Regulatory Review	2-1

2.1	National Legislation	2-1

2.3	WB Safeguard Policies	2-3

3	Project Description	3-1

3.1	Project Development Objective	3-1

3.2	Project Components	3-1

3.3	Implementation	3-6

4	Potential Environmental Impacts and Mitigation	4-1

4.1	Environmental Screening	4-1

4.2	Environmental Impacts	4-1

4.3	Mitigation Measures	4-4

4.4	Residual Environmental Impacts	4-7

5	Institutional and Implementation Mechanism	5-1

5.1	Institutional Arrangements	5-1

5.2	Implementation Arrangements	5-3

5.3	Legal and Contractual Arrangements	5-5

6	Environmental Monitoring	6-1

6.1	Objective	6-1

6.2	Environmental Monitoring Framework	6-1

6.3	Monitoring Indicators	6-2

7	Environmental Trainings and Awareness Raising	7-1

7.1	Objectives	7-1

7.2	Type of Environmental Trainings	7-1

7.3	Training Need Identification and Module Development	7-1

7.4	Initial Trainings	7-2

7.5	Subsequent Trainings	7-2

7.6	Environmental Awareness Raising	7-2

8	Communication and Documentation	8-1

8.1	Objectives	8-1

8.2	Communication	8-1

8.3	Documentation	8-2

9	Environmental Management Cost	9-1

List of Attachments

Attachment ‎2.1:  Wetlands in Afghanistan	2-6

Attachment ‎4.1:  Screening Matrix (Un-mitigated)	4-8

Attachment ‎4.2:  Comparison of Disposal Methods for Animal Wastes Generated from Avian Influenza Outbreaks 	4-9

Attachment ‎4.3:  Mitigation and Monitoring Plan 	4-15

Attachment ‎4.4:  Residual Impacts	4-21

Attachment ‎5.1:  Roles and Responsibilities	5-6

Attachment ‎5.2:  ToR for International Environmental and Waste Management Consultant	5-9

Attachment ‎5.3:  ToR for Environmental Focal Point (Animal Health)	5-11

Attachment ‎5.4:  ToR for Environmental Focal Point (Human Health)	5-12

Attachment ‎5.5:  Implementation Schedule	5-13

# Introduction

The Islamic Republic of Afghanistan is embarking upon the Avian Influenza Control and Human Pandemic Preparedness and Response Project (Avian Influenza – AI project for short).  The project is funded by the World Bank (WB).  In line with the national legislative requirement and WB’s safeguard policies, an environmental management plan (EMP) of the AI project has been developed.  This document presents this EMP.

## Background

Outbreaks of highly pathogenic avian influenza (HPAI) caused by the H5N1 subtype of influenza “A” were first recognized in Hong Kong in 1997.  Since late 2003, this subtype has been spreading at an alarming rate, from East Asia to Central Asia, and now to the Middle East, Europe, Africa, and South Asia.  In addition to its impact on animal health, with millions of domestic poultry having died or been destroyed worldwide, H5N1 has been causing severe human disease.  Of the known 258 humans with confirmed HPAI as of November 2006, most (154) have died.  The rapidly expanding area in which HPAI has been discovered and the escalating number of human infections have raised concerns worldwide over the possible evolution of the next influenza pandemic and its disastrous consequences.

As a result of a quarter-century of devastating civil strife and half a decade of serious drought, Afghanistan has some of the poorest social, economic and health indicators in the world with high susceptibility to communicable diseases.  Inadequate facilities and capacities to detect, control, contain and mitigate an outbreak of communicable disease have made this country highly vulnerable.  Twenty-six confirmed cases of H5N1 virus in sampled chicken in four provinces have been reported since testing started in March 2006.  The virus – which was first diagnosed in the province of Nangahar - appeared to be spreading fast, with infection occurring in five new provinces in close succession (Kabul, Laghman, Logar, Parwan and Kapisa).  However, since bird migration stopped in May, there have been no further outbreaks of animal and human influenza disease (AHID) in Afghanistan.  Bird migration will normally restart by October and preparedness will be particularly important during the following six months.

In March 2006, an inter-sectoral Task Force prepared a National Avian Influenza and Influenza Pandemic Preparedness and Response Plan (ANIPPRP) formally endorsed by the Government of Afghanistan (GoA).  After preparing the plan, the Government requested the World Bank assistance to finance the Plan.  The ANIPPRP provides a strong basis on which to detect and combat possible outbreaks, and outlines the institutional mechanisms for doing so.  The plan is candid about what capacity and resource constraints exist.  The ANIPPRP was later supplemented with an Operational Plan, which formed the basis for the World Bank appraisal.

Under the Plan the Ministry of Agriculture, Irrigation and Livestock (MAIL) adopted a policy of slaughtering birds in the vicinity of all proven outbreaks of H5N1 and payment of compensation to farmers concerned.  This policy was initiated under the FAO supported Avian Influenza Response Project (AIRP) and, as a result of the 26 diagnosed cases, about thirty thousand birds were slaughtered.  Since then, eight regional emergency centers have been established for handling AI (Kabul, Nangahar, Kandahar, Herat, Bamayan, Balkh Kunduz and Ghazni).  Intensive training has been provided to provincial veterinary directors and training courses on AI awareness have been organized for 285 veterinarians.  Initial supplies of equipment, protective clothing and flu detector antigen have been distributed and a surveillance program has been initiated based on 2 percent monthly sampling of poultry flocks in each regional center.

## Project Operational Manual

The Project Operational Manual (POM) has been developed in order to provide detailed procedures and guidelines for the implementation of the AI project.  The POM describes the implementation arrangements, and defines roles and responsibilities of the implementing agencies.

The present EMP is one of the annexures of the POM.

## EMP Objectives

The overall objective of the EMP is to improve the environmental performance of the project, and to ensure that the proposed activities do not cause an unacceptable level of environmental impacts or public health risks.  Specifically, the EMP will perform the following functions:

Meet the requirements as given in the national environmental law as well as the WB safeguard policies.

Facilitate the implementation of the environmental mitigation measures (discussed later in the document).

Define implementation and organizational arrangements, as well as roles and responsibilities of various members of the project team with regard to environmental management.

Define the environmental monitoring mechanism and identify monitoring parameters in order to:

Ensure the complete implementation of all mitigation measures, and

Ensure the effectiveness of the mitigation measures.

Identify environmental training requirements at various levels.

Define the communication and reporting protocols for environmental management.

The EMP will also help in mainstreaming the environmental management in the routine activities, and capacity building of the personnel, in the implementing ministries (MOPH and MAIL).

## Methodology

A generic EMP existed at the project development and appraisal stage.  Before the initiation of the project activities, and simultaneous to the development of the POM, the present EMP was developed.  An effort was made to make the EMP relevant to the local conditions and existing capacities within the implementing ministries.  The specific activities carried out while developing the present EMP are briefly described below.

Review of the project details:  Various components of the Afghanistan AI project were studied, in addition to other background material.

Discussions with project personnel:  Discussions were held at the WB project team (task team) as well as the team developing the POM, in order to understand the project context, implementation plans.  Similar discussions were held with relevant officials within MAIL and MOPH, in order to understand their expected role in the project, and the existing environmental management capacity and capability.

Separate meetings were held with MAIL and MOPH in order to identify the possible environmental focal points for the AI project.

One of the objectives of these meetings was to determine the environmental training needs of various project personnel.

Meeting with NEPA:  A meeting was held with the NEPA officials, in order to apprise them of the proposed project activities and the process of developing the present EMP.

Meeting with UNEP:  A meeting was held with UNEP in Kabul, in order to understand their possible role in developing the EMP, and during the project execution.

Field visits:  Short field visits were carried out to the areas where AI outbreaks occurred in the past.  These included two communities within Kabul (Shah Shaheed and Dasht Berchie), and a community near Mahmood Raqi (Kapisa province).  The objectives of these visits were to see the type of communities affected, carcass disposal sites, awareness level of the communities, and status of the compensation payment.

EMP compilation:  With the help of information and data collected during the above steps, the present EMP was compiled.  The EMP structure, discussed in the following section, follows the WB safeguard policies as well as the internally acceptable ‘industry’ practice.

## EMP Components

The present EMP has the following components:

Regulatory Review (Section 2):  It provides brief description and their applicability of the relevant national environmental legislation, as well as the WB safeguard polices.

Project Description (Section 3):  This section provides brief description of the Afghanistan AI project.

Potential Environmental Impacts and Mitigation (Section 4):  The environmental and public health risks that the proposed project may pose are discussed in this section, along with the associated mitigation measures.

Institutional and Implementation Arrangements (Section 5):  This section defines the institutional arrangements, roles and responsibility, and implantation procedures for the environmental management of the AI project.

Environmental Monitoring (Section 6):  This section provides the environmental monitoring framework.

Environmental Trainings (Section 7):  The environmental training plan is provided in this section.  The plan identifies the type of trainings, training contents, trainers and trainees, and training schedule.

Communications and Documentation (Section 8):  The communication, documentation and reporting protocol is provided in this section.

Environmental Management Budget (Section 9):  Finally, the cost of environmental management is discussed at the end of the document.

# Regulatory Review

This section provides an overview of the Afghanistan’s environmental legislation, and their relevance to the AI project.  Also provided in this section is a summary of the WB safeguard policies and their compliance/triggering status for the project.

## National Legislation

The environmental law in Afghanistan has recently been enforced, through the official gazette No. 912, dated 25 January 2007, after being approved by the Parliament.  “This Act has been promulgated to give effect to Article 15 of the Constitution of the Islamic Republic of Afghanistan, and provide for management of issues relating to rehabilitation of the environment and conservation and sustainable use of natural resources, living organisms and non-living organisms.”

The Act is divided in nine chapters, listed below:

General Provisions

Functions and Powers

Management of Activities affecting the Environment

Integrated Pollution Control

Environmental Considerations Relevant to Water Resource Conservation and Management

Biodiversity and Natural Resource Conservation and Management

Environmental Information, Education and Training and Research

Compliance and Enforcement

Miscellaneous Orders.

The salient provisions of the Act relevant to the AI project are briefly discussed below.

Institutions:  The Act defines the functions and powers of the National Environmental Protection Agency (NEPA), which is the prime environmental regulatory and approval authority in the country.  Through the Act, the Committee fro Environmental Coordination has been established, in order to promote integration and coordination of environmental issues and the fundamental principles set out in the Act.  The Committee will be composed of the representatives of all relevant ministries, national institutions, Provincial Councils, District Councils, Village Councils and civil society organizations.  In addition, the National Environmental Advisory Council has also been established, in order to advise the NEPA on regulatory, environmental and financial matters.  The Act also calls for establishment of the Sub-national Environmental Advisory Councils in every province, in order to make recommendations regarding environmental and financial matters.

Environmental Management:  Under the Act, the proponents of any project, plan, policy or activity must submit to NEPA a Preliminary Environmental Assessment, in order to allow NEPA to determine the associated potential adverse effects and possible impacts.  After reviewing the preliminary assessment, NEPA can either authorize - with or without conditions – the project, plan, policy or activity, provided that the potential adverse effects of the proposed activities on the environment are unlikely to be significant.  Otherwise, NEPA may require the proponents to submit a detailed environmental impact statement including a comprehensive mitigation plan for its review and approval.

The present EMP will be submitted to NEPA in pursuance with this provision of the Act.

Pollution Control:  The Act defines the requirement and procedure for obtaining the pollution control license for any facility which discharges any pollutant into the environment, if the discharge causes or likely to cause significant adverse effect on the environment or public health.  Similarly the Act describes similar requirements and procedures for hazardous waste management license.

During the operationalization of the EMP (discussed later in the document) this aspect will be discussed with NEPA, particularly with reference to requirement of the pollution control license for the hospitals and laboratories supported by the AI project.

Biodiversity and Natural Resources Conservation/Management:  The Act identifies the need to develop the national biodiversity strategy.  The Act also establishes the national protected areas system, under which NEPA will develop comprehensive plan for the national protected areas.  Subsequently, the protected areas will be selected and delineated in consultation with the relevant ministries and local communities.

During the EMP operationalization, this aspect will also be discussed with NEPA, with regard to its implication on the AI project (ie, the project activities in an area which will in future be included in any protected area).

Other National Regulations and Policies under Development

The national environmental legislation has been promulgated, however several regulations, guidelines and policies are still needed, in order to provide detailed procedures for complying with the law.  The following documents are in the process of development:

Interim Environmental Impact Assessment Regulations

Environmental Impact Assessment Policy

Administrative Guidelines for EIA

Protected Areas Regulation.

All of the above regulations, guidelines and policies are likely to be relevant to the AI project.  During the EMP operationalization, their relevance to the project will need to be discussed with NEPA, particularly if by then these instruments are finalized and officially notified.

## WB Safeguard Policies

The project has also been analyzed against the WB safeguard policies: OP 4.01 (environmental assessment), OP 4.04 (natural habitat), OP 4.36 (forestry), OP 4.09 (pest management), OP 4.11 (cultural property), OP 4.10 (indigenous people), OP 4.12 (involuntary resettlement), OP 4.37 (safety of dams), OP 7.50 (projects in international waters), and OP 7.60 (projects in disputed areas).  These policies and their applicability for the AI project are briefly introduced below.

### Environmental Assessment (OP 4.01)

The World Bank requires environmental assessment (EA) of projects proposed for Bank financing to help ensure that they are environmentally sound and sustainable, and thus to improve decision making.  The OP defines the EA process and various types of the EA instruments.

The Bank classifies the proposed project into one of four categories, depending on the type, location, sensitivity, and scale of the project and the nature and magnitude of its potential environmental impacts.

(a) Category A:  A proposed project is classified as Category A if it is likely to have significant adverse environmental impacts that are sensitive, diverse, or unprecedented.  For a Category A project, the borrower is responsible for preparing a report, normally an EIA (or a suitably comprehensive regional or sectoral EA).

(b) Category B:  A proposed project is classified as Category B if its potential adverse environmental impacts on human populations or environmentally important areas—including wetlands, forests, grasslands, and other natural habitats—are less adverse than those of Category A projects.  These impacts are site-specific; few if any of them are irreversible; and in most cases mitigatory measures can be designed more readily than for Category A projects.  The scope of EA for a Category B project may vary from project to project, but it is narrower than that of Category A EA.

(c) Category C: A proposed project is classified as Category C if it is likely to have minimal or no adverse environmental impacts.  Beyond screening, no further EA action is required for a Category C project.

(d) Category FI: A proposed project is classified as Category FI if it involves investment of Bank funds through a financial intermediary, in subprojects that may result in adverse environmental impacts.

Compliance Status:  The AI project is categorized as Category B.  The proposed activities are expected to generate no or limited adverse environmental effects, since most activities are designed to support preventive measures.  The Project will, generally, have positive environmental and social impacts as investments in facilities, equipment, laboratories, and training will improve the effectiveness and safety of existing avian influenza handling and testing procedures.

The generic EMP that existed at the project appraisal stage, and the present adapted and expanded EMP, have been developed in response to this OP.

### Involuntary Resettlement (OP 4.12)

Involuntary resettlement under development projects, if unmitigated, often gives rise to severe economic, social, and environmental risks.  OP 4.12 provides safeguards to address and mitigate these impoverishment risks.

Compliance Status:  This OP is not triggered, since involuntary resettlement or land/asset acquisition is not included in the AI project.  The hospitals/clinics supported under the project will be rehabilitated on the existing premises, thus avoiding any land take.  The carcass burial will be carried out at state land as far as possible, or at the community land with the full consent of the concerned community, and transfer of land will not take place.

### Natural Habitat (OP 4.04)

The conservation of natural habitats, like other measures that protect and enhance the environment, is essential for long-term sustainable development.  Through this OP, the Bank therefore supports the protection, maintenance, and rehabilitation of natural habitats and their functions.

Compliance Status:  This OP is not triggered, since the project activities are unlikely to change the natural habitat.  The activities that may have any interaction with the natural habitat/wildlife are the surveillance, catching, culling or disposal of wild birds, particularly near the wet lands (see Attachment 2.1 for the known wetland in the country).  To mitigate the potential adverse impacts, these activities will be carried out in coordination and consultation with the relevant departments (NEPA and Forestry Department in MAIL); the surveillance and culling carcass activities will be carried out in a manner to have no significant impact, if at all, on the natural habitat/wild life of the area; and disposal sites will be selected in a manner that the wetlands are not adversely impacted.

### Forestry (OP 4.36)

The objective of this Policy is to assist the WB’s borrowers to harness the potential of forests to reduce poverty in a sustainable manner, integrate forests effectively into sustainable economic development, and protect the vital local and global environmental services and values of forests.

Compliance Status:  This OP is not triggered, since the project activities are unlikely to affect the forest resources.  Most of the carcass burial during the project is likely to be near the community, outside any forests.  In case of culling of the wild birds, it is however possible that the burial site is inside the forest.  However, such activities will be carried out in coordination with the concerned departments, and maximum care will be employed in site selection and restoration after the burial.

### Pest Management (4.09)

Through this OP, the WB supports a strategy that promotes the use of biological or environmental control methods and reduces reliance on synthetic chemical pesticides.

Compliance Status:  The project does not support procurement or usage of any pesticides.  Hence this OP is not triggered.

### Safety of Dams (OP 4.37)

The Policy seeks to ensure that appropriate measures are taken and sufficient resources provided for the safety of dams the WB finances.

Compliance Status:  The project does not involve any work related to dams.  Hence this OP is not triggered.

### Projects on International Waterways (OP 7.50)

This OP defines the procedure to be followed for projects the WB finances that are located on any water body that forms a boundary between, or flows through two or more states.

Compliance Status:  This OP is not relevant to the project, since the project activities do not involve any work related to the international waters.

### Indigenous People (OP 4.10)

This OP defines the process to be followed if the project affects the indigenous people.  The policy requires that the proponents will develop an Indigenous People Development Plan and get it approved by the Bank, if such groups are identified during the project implementation.

Compliance Status:  No indigenous people - with a social and cultural identity distinct from the dominant society that makes them vulnerable to being disadvantaged in the development process – are known to exist in the areas where different project components would be located.  Therefore this OP is not triggered.  However if such groups are identified during the project implementation, the proponents will develop an Indigenous People Development Plan, in compliance with the OP and get it approved by the Bank.

### Cultural Property (OP 4.11)

The World Bank’s general policy regarding cultural properties is to assist in their preservation, and to seek to avoid their elimination.  Under this OP, the Bank normally declines to finance projects that will significantly damage non-replicable cultural property, and will assist only those projects that are sited or designed so as to prevent such damage.

Compliance Status:  No project activities are likely to affect or damage the cultural property.  During the selection of the carcass disposal sites, it will be ensured that there exist no archeological, cultural, historical or religious remains/artifacts at or in the immediate vicinity (this aspect will be included in the guidelines for the burial site selection).  In case of discovery of such sites of archeological, cultural, historical or religious significance during the excavation for the burial pits, the work will be stopped (burial will be carried out at any alternate location), and the concerned department will be notified about the discovery.

### Projects in Disputed Areas (OP 7.60)

In accordance with this Policy, the Bank may proceed with a project in a disputed area if the governments concerned agree that, pending the settlement of the dispute, the project proposed for country A should go forward without prejudice to the claims of country B.

Compliance Status:  No project activities will be carried out in any disputed territory, hence this OP is not triggered.

Attachment 2.1:  Wetlands in Afghanistan

Afghanistan is an arid country and the few wetlands that do exist are therefore of great significance to biodiversity.  Wetlands provide habitat for many migrating water birds.  Wetlands are also teeming with numerous species of aquatic plants and invertebrates, fish, and amphibians.  Artificial lakes are generally not as ecologically valuable as natural lakes because of fluctuating water levels and because natural plant and animal assemblages have not had time to develop.  Nevertheless, they can provide important habitat for some species.   The table below lists the Afghan wetlands that are known or suspected to be important for biodiversity.  Examination of an Afghanistan map suggests that there are other wetlands that could be investigated for ecological significance.

| Wetland Name | Wetland Type | Location | Province | Source |
| --- | --- | --- | --- | --- |
| Hamun-i-Puzak | Natural lake and marsh | 31° 29' 44" N; 61° 42' 55" E | Farah | Sayer and Van der Zon (1981), Scott 1995 |
| Hamune Saburi | Natural lake and marsh | 31° 31' 24" N; 61° 17' 23" E | Farah | K. Habibi (pers. com. 2006) |
| Arghandab Reservoir | Artificial lake | 31º 51' 21" N, 65º 53' 45" E | Kandahar | Sayer and Van der Zon (1981) |
| Kajaki Reservoir | Artificial lake | 32° 19' 59" N, 65° 11' 07" E | Helmand | Sayer and Van der Zon (1981) |
| Ab-i-Estada | Natural saline lake | 32° 28' 53" N, 67° 54' 36" E | Ghazni | Sayer and Van der Zon (1981); Scott 1995 |
| Dashte Nawar | Seasonal saline lake | 33° 38' 00" N; 67° 43' 05" E | Ghazni | Sayer and Van der Zon (1981); Scott 1995 |
| Sardeh Reservoir | Artificial lake | 33° 29' 37" N; 68° 28' 22" E | Ghazni | Sayer and Van der Zon (1981) |
| Qargha Lake | Artificial lake | 34° 33' 18" N; 69° 01' 59" E | Kabul | Sayer and Van der Zon (1981) |
| Kol-i-Hashmat Khan | Natural lake and reed swamp | 34° 29' 29" N; 69° 12' 13" E | Kabul | Sayer and Van der Zon (1981); Scott 1995 |
| Darunta Lake | Artificial lake | 34° 29' 31" N; 70° 21' 34" E | Nagarhar | Sayer and Van der Zon (1981); Scott 1995 |
| Sarobi Lake | Artificial lake | 34° 23' 55" N; 69° 41' 33" E | Kapisa | Sayer and Van der Zon (1981); Scott 1995 |
| Darqad | Swamp woodlands on Amu Darya | 37° 26' 39" N; 69° 32' E | Takhar | Sayer and Van der Zon (1981); Scott 1995 |
| Imam Sahib | Swamp woodlands on Amu Darya | 37° 12' 22" N ; 68° 44' 46" E | Kunduz | Sayer and Van der Zon (1981); Scott 1995 |
| Band-i-Amir | Six natural lakes | 34° 52' 40" N; 67° 16' 51" E | Bamiyan | Sayer and Van der Zon (1981); Scott 1995 |
| Dagh-i-Tondi | Intermittent lake | 32° 27' 41" N; 60° 56' 49" E | Farah | K. Habibi (pers. comm.) |
| Kowl-i-Namaksar | Salt lake | 34° 04' 11" N; 60° 39' 56" E | Herat | K. Habibi (pers. comm.) |
| Gawde Zereh | Seasonal lake | 29° 43' 44" N; 61° 42' 41" E | Nimroz | K. Habibi (pers. comm.) |
| Zor Kol | High mountain lake | 37° 25' 54" N; 73° 43' 04" E | Badakhshan | Scott (1995) |
| Chaqmaqtin | High Mountain lake | 37° 13' 48" N; 74° 10' 29" E | Badakhshan | Scott (1995) |
| Ay Khanum | River, Marshy reedbeds, small ponds, and grassy meadows | 37° 12' 17" N; 69° 26' 35" E | Darqad | Khan (2005) |
| Weghnon | High mountain lake | 36° 01' 45" N; 74° 00' 45" E | Takhar | Khan (2005) |

# Project Description

This section provides a simplified version of the project description (the complete description is available in other project document including Project Operational Manual.

## Project Development Objective

The overall objective of the Project is to minimize the threat posed by HPAI to humans in Afghanistan by controlling such infections among birds, especially domestic poultry, and preparing for, controlling, and responding to possible human infections, especially an influenza epidemic and related emergencies.  Though the objective is specific to HPAI, the interventions are expected to contribute to the control of other zoonotic diseases and other types of infectious diseases, in terms of building overall response capacity.

This objective will be achieved through three types of interventions: (i) prevention; (ii) preparedness and planning; and (iii) response and containment.  If these types of interventions achieve their goals, the proposed project will reduce the burden of disease in animal and the consequent economic losses.  It will also lower the risk of human infection and the loss of productivity attributable to human infections in Afghanistan.  Finally, it would limit the risk of HPAI in other countries.

At the end of the project it is expected that (i) the capacity of the agencies involved in AI containment, control and mitigation will have significantly improved; (ii) the threat to human health in the high risks provinces of Afghanistan will have been substantially reduced; and (iii) the general public will be aware and will have adopted AI related human, animal health and environmental safeguards.

## Project Components

The project will finance activities under four components:

Animal Health

Human Health,

Communications and Public Awareness, and

Institutional Coordination and Project Management.

These components are discussed below.

### Animal Health

Under the responsibility of the Animal and Plant Health Department of the Ministry of Agriculture and Irrigation, this component will support a national program to develop and implement HPAI prevention, containment, control, and eradication activities in the livestock sector of Afghanistan creating an effective system for improved bird health surveillance, diagnostic analysis and disease control in accordance with FAO/OIE standards.

The key elements of this component are described below.

#### A.1.  Strengthening HPAI Control and Outbreak Containment Capacity

A.1.a.  In support of efforts to control and contain the avian influenza emergency situations, the Project will support eight regional ERTs.  Each Team will be composed of four veterinarians, who will be equipped with all necessary material to carry out field investigation and culling operations.  The provisional list of minimum required equipment is as follows: rapid tests, personal protection equipment sets (PPEs), disinfectants, sprayers, motorized mist blowers, autopsy kits, culling bags, CO2 cylinders, GPS, cell phones, maps, laboratory equipment for samples collection, storage (refrigerators and freezers) and sample transportation (liquid nitrogen tanks and cool boxes).

ERTs in five ‘at-risk’ zones will be recruited within the first month of project effectiveness. The remaining ERTs in the rest of the zones shall be recruited no later than the 5th month after project effectiveness.  The Project Coordinator (PC), Animal Health Coordinator and the Zone Coordinator with the assistance of the Provincial Department of Agriculture (PDA) shall recruit the ERTs. In addition to the hired members of the ERTs, some staff of the PDA, in particular the district veterinarians shall also be part of the ERTs.

A.1.b.  Training for the ERTs.  Teams will be provided with technical operation manuals on samples collection, storage and transportation, outbreaks investigation, methods for culling and disposal of carcasses.

A.1.c.  Field simulation exercises will be organized for ERTs to check if emergency procedures could be duly implemented.

A.1.d.  Procurement of vaccine for emergency and regular vaccination programs in the commercial and semi-commercial sector. It is estimated that a maximum of 6,000,000 doses of vaccines shall be necessary for the duration of the project life.

A.1.e.  Establishment and implementation of procedures to monitor the efficacy of the vaccine and to establish a monitoring program in commercial vaccinated flocks in order to be able to detect early incursions of the virus.

A.1.f.  The project will procure a number of station wagons, pick ups, motor bicycles and truck in order to carry out timely and effectively above mentioned activities in the country.

#### A.2. Human Safety Assurance

A.2.a.  Extensive training activities will be carried out by ERTs for field veterinarians, field staff and farm workers on recognition of avian influenza and procedures of self-protection in case of handling suspected birds.  Training will include the procedures of activation of the ERTs. Each ERT will carry out three training sessions per year in order to cover the relevant satellite provinces.

A.2.b.  Provision of PPEs for the ERTs, trainees, and State Veterinary Department (SVD) staff.  The Project will procure 10,000 (ten thousand) units composed of coveralls, boots, head-covers, masks, goggles and gloves.

#### A.3.  Strengthening HPAI clinical and laboratory diagnosis and surveillance for rapid and effective outbreak detection and containment capacity

A.3.a.  Training and review the regulatory and legislation framework and development of guidelines for compensation scheme.

A.3.b.  Improvement of information system is an essential component of the surveillance system, which will be enhanced through the procurement of different items aimed at improving the capacity of the State Veterinary Department to rationalize information collected through surveillance system.  Training will also be provided on the implementation of an ad-hoc information system.

A.3.c.  In order to strengthen disease surveillance capacity, training and preparation of guidelines and manuals will be provided for investigating diseases in the sub-component identified (rural, commercial and semi-commercial sectors, live bird markets and wetlands).

A.3.d.  Field veterinarians involved in surveillance activities in wetlands will undertake a training course on sample collection and recognition of wild bird species, which are relevant to AI epidemiology.

A.3.e.  The Central Veterinary Diagnostic Laboratory in Kabul will be provided with laboratory equipment, reagents and consumables in support of surveillance activities.  Laboratory staff involved in diagnosis will undertake refreshing training courses on laboratory techniques.

#### A4. Improving Bio-Security in Poultry Production

Bio-security is perhaps the cheapest and most effective means of disease control available. No disease prevention program will work without it.  Bio-security is a concept for prevention of disease entry/escape that must be practiced by all farmers, cooperatives, abattoirs, transporters and retailers.  Lack of bio-security measures increases the risk of introducing disease or infection into the production unit, market, or any commercial operation.  Farm management practices and marketing systems influence the probability of poultry being challenged (and becoming infected) with HPAI.

FAO, as part of its contract, will conduct studies to assess current levels of bio-security and impact assessments, preparation of manuals in bio-secure poultry production and marketing systems in backyard and semi-commercial systems.  The guidelines and relevant manuals would address bio-security issues from production to retailing.  The guidelines and manuals will be direct inputs to the WB-funded Horticulture and Livestock Project (HLP), which has a poultry production component.

#### A.5. Compensation facilities

The project will establish a compensation fund for farmers in order to reimburse them from the loss of domestic poultry due to HPAI.

#### A.6. Technical Assistance – International Consultants

International consultants will be recruited to provide technical expertise to national staff throughout the project.

#### A.7. Waste Management and Sanitation

This sub-component will include the preparation of a national plan, standard guidelines and an operational manual for HPAI-related waste management, as well as equipment and supplies to support healthy and environmentally friendly disposal of culled animals, laboratory waste disposal and decontamination.

### Human Health

Under the direction of the Ministry of Public Health (MOPH), this component will support a national program of activities to prevent, detect, respond to and mitigate the impact of human illness caused by avian or pandemic influenza.  Component activities will involve emergency and long-term developments to address priority gaps in disease surveillance, control and treatment.  It would also contribute to MOPH’s ongoing program for re-establishing public health capacity that was destroyed during decades of conflict.

The key elements of this component are described below.

#### B.1. Program Planning and Coordination

B.1.a.  Recruitment of HH Coordinator and Command and Control Unit (CCU) Director.

B.1.b.  Development of protocols and guidelines.  The AI guidelines have already been prepared by the World Health Organization (WHO) in English and translated in Dari; a team is working to translate this document in Pashto.  The USAID AI-related funds have been used to develop and translate these guidelines.

B.1.c.  Training (surveillance personnel, Emergency Response Teams, health care workers, simulation exercises).  The Afghan Public Health Institute (APHI) has developed a detailed training plan for the training of relevant stakeholders involved in the control and management of the Avian Influenza cases and outbreaks.  Seventeen surveillance personnel from the Disease Early Warning System (DEWS) in eight regions of the country have been trained. The training was for one week and the issues which were covered were orientation to AI surveillance, AI case investigation and management, which were conducted by WHO and APHI.  These activities were financed through the USAID/WHO AI-related funding.  The DEWS officers have established 6-7 sentinel sites in each of the eight provinces and plan to train the DEWS focal points in subsequent priority provinces.

#### B.2. Strengthening Disease Surveillance

B.2.a.  MOPH Surveillance Unit will be established.  Activities involved include recruitment of staff- surveillance director and IT coordinator, procurement of communication equipment, furniture, computers, establishment of flue sentinel sites and procurement of pick ups.

Eight regional flue sites have already been established in the eight regional centers, which include Kabul, Nangarhar, Paktia, Kandahar, Herat, Balkh, Badakhshan and Bamyan provinces.  At least 5-6 sentinel sites in each of these provinces have been established and partially equipped by WHO.  The project funds will be used to fully equip these sites and finance the recruitment of an AI coordinator.

B.2.b.  National and Provincial Emergency Response Teams (ERT).  In order to build a sustainable structure for preparedness and response to the suspected AI outbreaks in the country, APHI has trained 11 Emergency Response Teams (ERT) in the high risk provinces in the country.  Each team consists of the CDC focal point, a Lab technician and a veterinarian.  The teams are coordinated at the regional level by the DEWS regional officers.  All ERTs have been equipped with PPE kits, thermometers, forms and other necessary equipment to conduct case investigations.

The APHI/MOPH plans to train 5-10 National ERTs in the country as back up and support to the Provincial ERTs, with the aim to strengthen the national emergency response system in the country.  In addition, at least 23 other ERTs will be trained for 23 remaining provinces as part of the project activities.  APHI will need the support of its international partners to expand the curriculum for training and further technical assistance will also be necessary to train trainers and support regional training activities.  Therefore, a more elaborate training manual and guidelines need to be prepared and relevant training should be provided to the ERTs.

#### B.3. Health Care System Capacity

B.3.a. National and regional referral centers.  MOPH has designated 8 hospitals to have isolation wards for suspected AI case management.  These wards are located in the 8 hospitals in 7 provinces of the country, namely Kabul (Indra Ghandi and Infectious Disease Hospitals), Nangarhar, Kandahar, Balkh, Badakhshan, Bamyan and Herat.

The following activities are envisaged under the health care system capacity improvement:

Renovation of the two selected hospitals in Kabul with enhanced bio-security measures (installation of ventilation equipment, incinerators and partitioning patient rooms), using the CDC fund.

The two hospitals in Balkh and Herat provinces only require renovation since the buildings are relatively less damaged.  The allocated project financing shall be utilized to renovate these wards with enhanced bio-security enhanced.

Substantial rehabilitation and furnishing is necessary for the selected hospitals in the remaining five provinces as the hospital buildings have been severely damaged.

B.3.b.  Establishment of a warehousing capacity for project.  Warehouse capacity is nearly non-existent in the APHI and very limited elsewhere in the MOPH.  The central MOPH warehouse will be renovated as part of this component.

B.3.c.  Procurement of PPE kits, antiviral and antimicrobial medications, seasonal flu vaccines and Rapid Diagnostic kits.

B.3.d.  Surge mechanism, pandemic case management, social distancing.  Two separate workshops will be conducted and an international facilitator will be invited/hired to facilitate this process. Participants will be invited from different sectors, ministries, NGOs and UN organizations.

### Communication and Public Awareness

Under the coordination of the communications specialist based at the AI Secretariat, and with the advise and technical assistance of the Communications Task-Team (including donors, and NGOs), the communications component will finance baseline research, design, test and implementation of a comprehensive and integrated communications strategy, to:

elevate public awareness and promote behavior-change among at-risk and vulnerable populations, to control the spread of the virus;

provide visibility to the multi-sectoral response, and generate a sense of transparency and trust;

maintain high-level political engagement during the different pandemic phases; and

build upon the available communications infrastructure of various ministries and stakeholders, to foster an "enabling environment," where the community at large understands the possible threat, adopts preventive behaviors, supports programmatic activities, contributes with the reporting, social monitoring and self-reliance mechanisms.

### Implementation Support

This component will support the institutional coordination and management of the Project. There will be no formal Project Implementation Unit, but staff within the MAI and MOHP would be assigned to a core support team to handle key functions including financial management, procurement, and monitoring and evaluation of Project activities, as well as compliance with the agreed environmental management framework.  The central coordination of the project will be in the Planning and Policy Department (PPD) of the Ministry of Agriculture and Irrigation.  Provisions under this component will include goods, services and operating expenditures for coordinating/managing project implementation.

## Implementation

### Partnership Arrangements

In March 2006 as soon as the Ministry of Agriculture and Irrigation confirmed the existence of HPAI in the country, an inter-sectoral task force was established to prepare a National Avian Influenza Pandemic Preparedness and Response Plan (NAIPPRP).  The task force included representatives form Ministry of Agriculture, Irrigation and Livestock (MAIL), Ministry of Public Health (MOPH), Ministry of Commerce (MOC), Ministry of Finance (MOF), and National Agency for Environmental Protection (NEPA), representatives of concerned donors and implementing organizations such as FAO, USAID, USDA, EU, ADB, WB, WHO and UNICEF.  The preparedness plan has now been finalized and it provides the basis for the present AI project.

### Institutional Arrangements

Institutional arrangements are already in place and organized at central and field levels. They are consistent with GPAI standards in other countries.

#### Central Level

The main coordination entity for AI policies, strategy and action plans is the National AI Committee (NAIC) established in March 2006 under an inter-ministerial Cabinet level National Emergency Response Committee (NERC).  While the purpose of the NERC is to address country-wide coordination for any emergency, the NAIC focuses specifically on AI control and mitigation in the event of a major outbreak.  Headed by the Minster of Agriculture, the NAIC includes the Ministries of Public Health (MOPH), Rural Rehabilitation and Development (MRRD), Interior (MOI), and Commerce (MOC), as well as the National Environmental Protection Agency (NEPA).

The NAIC is advised by a Technical Committee chaired by the Director of Veterinary Services of MAI which provides overall technical knowledge and shares data and information on AI.  The Technical Committee is composed by representative of the technical department of the interested government agencies.  WHO, UNICEF, FAO, US Department of Health and Human Services, Centers for Disease Control and Prevention (HHS/CDC), several non-governmental organizations, World Bank, European Commission, DFID and USAID are also participating members.

By the same token a Financial Committee chaired by the Deputy Minister of Finance advises NAIC on financial and budget issues related to AI activities, including annual budget allocations, coordinates and alignment of donor resources, and cash flow projections.

#### Field Level

Provincial AI Committees (PAICs) chaired by the Provincial Governor, coordinate and manage AI activities in the respective provinces.  Members of the PAIC include provincial representatives of MAI (Veterinary Services Division), Department of Public Health, Municipality, the Police Department, the border police (where relevant), MRRD and NEPA. The technical members of the PAIC will ensure that implementation of the various components of the project are in accordance with the stipulated standards, norms, rules and regulations – not only technical but also social and cultural.  The implementation at field level will be the responsibility of the provincial and district level public health staff and veterinary staff with assistance from the staff of WHO, FAO, UNICEF, other multi- or bi-lateral support agencies, Veterinary Field Units (VFU), Afghan Veterinary Association (AVA) and local NGOs.

### Implementation Arrangements

Overall and ultimate responsibility for project execution, successful implementation, accountability and outcomes will be with a newly established National Influenza Secretariat (NAIS), hosted in the General Department for Policy and Planning of the MAIL and integrated with an Implementation Support Team (IST) financed by the project and composed of locally and internationally recruited specialists.

The IST will include an overall Project Coordinator, an Animal Health Coordinator, a Human Health Coordinator, a Communications Coordinator, a Monitoring and Evaluation specialist, a GIS specialist, two Financial Management Specialists, two Procurement Specialists, and one Safeguard specialist.  Most of the IST will be physically located in the General Department for Policy and Planning (GDPP) of the MAI, while the Human Health Coordinator, Procurement Specialist, and Financial Management Specialist under the Human Health component will be based in the Directorate of Afghan Public Health Institute (APHI) of the MOPH. In addition, the NAIS will include limited supported staff.

The Project Coordinator will be nationally recruited and will report to the NAIS through the Director General of Livestock Services. The coordinators for each component will report to the NAIS through the Project Coordinator.

Activities under the Animal Health Component will be organized and supervised by an Animal Health Coordinator, who for technical functions of the project will work in collaboration with the Director of the Animal and Plant Health Department, MAI.  Under the responsibility of the Animal Health Coordinator, the implementation of the component will be contracted to an implementing partner, which is expected to be FAO - subject to agreement on the technical and financial terms and conditions, and acceptance of the Bank standard clauses on fraud, corruption and external audit.  Draft TORs for the Animal Health Coordinator have been completed.  Draft TORs for the hiring of FAO have been agreed at appraisal for the first year.

Activities under the Human Health Component will be organized and supervised by the Human Health Coordinator, who for technical functions of the project will work in collaboration with the relevant components of the MOPH.  The activities under the component will be outsourced to implementing partners, expected to be WHO and UNICEF, subject to agreement on the technical and financial terms and conditions, and acceptance of the Bank standard clauses on fraud, corruption and external audit.  Draft TORs for the hiring of WHO and UNICEF have been agreed at appraisal.

Activities under the Communications and Public Awareness Component will be coordinated and supervised by a Communications Coordinator, supported by the Communications Task-Team, and a short-term international consultant.  Communication activities will implemented mostly through a variety of partners and stakeholders, including the agricultural extension and health education teams of the MAI and MOPH, the communications infrastructure of the National Solidarity Program and Ministry of Education, NGOs working with media and community-radio, as well as UNICEF, if agreement on the technical and financial terms and conditions is reached, and subject to acceptance of the Bank standard clauses on fraud, corruption and external audit.  TORs for the hiring of technical assistance and the implementation of activities under the component have been agreed at appraisal.

# Potential Environmental Impacts and Mitigation

This section discusses the potential impacts of the project activities on the environment and public health.  Also provided in this are the mitigation measures to reduce if not eliminate these adverse impacts.

## Environmental Screening

As part of the environmental impact assessment process of the AI project, a screening matrix was developed - tailored specifically to the proposed project - focusing the potential environmental impacts that are likely to arise as a result of the project activities.  The matrix examined the interaction of the project activities with various components of the environment.  The impacts were broadly classified as physical, biological and social, and then each of these broad categories further divided into different aspects.  The potential impacts thus predicted were characterized in the matrix as follows:

High negative (adverse) impact,

Low negative impact,

Insignificant impact,

High positive (beneficial) impact,

Low positive impact, and

No impact.

The negative impacts predicted in this manner were the ‘unmitigated’ impacts.  Appropriate mitigation measures were recommended as part of this EMP, thus reducing the occurrence possibility and severity of the potentially adverse impacts.

The screening matrix is provided in Attachment 4.1.  The negative impacts identified in this matrix are discussed in the following section.

## Environmental Impacts

The potential adverse impacts of the project activities on environment and people are discussed below.

### Transportation of Viral Agents by Surveillance Teams

During the project execution, the surveillance teams may be exposed to the AI virus.  Improper handling of contaminated birds and bird products/wastes by these teams may transport and spread the disease, thus posing environmental as well as public health risks.  This transportation can take place through contaminated team members, equipment, clothes and vehicles.  The adverse impacts include the following:

Health hazard for the surveillance team members themselves.

Health hazard for other people who come in contact with the team members or the contaminated clothes, equipment and vehicles.

Spread of disease to other areas/poultry/wild bird populations.

Contamination of air, soil and water caused by the contaminated personnel, clothes, equipment and vehicles.

The above threats exist during the surveillance of domestic/commercial poultry as well as for the wild birds.

### Handling, Culling and Transport of Infected and At-risk Birds

Much like the potential adverse impacts of the surveillance activities (discussed above), the handling, culling and transport of any contaminated birds, bird products or waste (eggs, manure and feathers) and equipment (for example in open containers) may also pose environmental and public health risks for the project staff as well as the communities.  The following specific environmental / public health risks are likely to exist during the culling and associated activities:

Health hazard for the culling team members (and other workers) themselves from the infected/dead birds, feathers, eggs, etc.

Health hazard for other people who come in contact with the team members or the contaminated clothes, equipment and vehicles.

Health hazard for the community

Health hazard associated with the handling of the culling agent (usually CO2 gas)

Spread of disease to other areas/poultry/wild bird populations during transportation of birds/carcasses.

Contamination of air, soil and water caused by the contaminated personnel, clothes, equipment and vehicles.

The above threats exist during the culling of domestic/commercial poultry as well as for the wild birds.

### Disposal of Carcasses

Improper system/method for disposing of dead birds may cause the spread of disease and contamination of air and water.  This may also pose public health risks for the project staff and the communities.  Various options are available for the safe disposal of carcass; these are tabulated in Attachment 4.2.  At this stage, the burial is considered to be the best option for Afghanistan, on the basis of the simplicity of burial process, low cost and availability of open spaces.

In addition to the potential adverse impacts associated with the culling operation discussed above, the following specific environmental / public health risks are likely to exist during the carcass disposal activities:

Contamination of soil, groundwater, surface water as a result of improper burial.

Health risk to the nearby population who may come in contact with the improperly disposed carcasses and other infected materials (eggs, feathers, disposable PPEs, etc.)

Spread of disease to new (un-infected) areas if the disposal site is away from the infected/culling site.

Blockage of natural drainage resulting from inappropriate selection.

Soil erosion resulting from improper backfilling and redressing the burial pit, and/or inappropriate site selection.

Safety hazard for the project staff and community resulting from improper backfilling of the pit, or keeping the pit uncovered for extended period of time.

Damage to crops resulting from improper site selection for the burial pit.

Blockage of existing routes resulting from improper site selection for the burial pit.

Damage to natural flora and fauna, forests and wetlands, resulting from inappropriate burial site selection (eg, inside forests, or near wetlands).

Damage to sites of archeological, cultural, historical or religious significance.

### Decontamination

Improper decontamination procedure may expose project staff as well as the community to the decontaminant agents.  These can be summarized as follows:

Spread of disease as a result of improper/inadequate decontamination.

Health risk (intoxication) for the project staff carrying out the disinfection.

Health risk for the community where the decontamination is carried out.

Contamination of soil and water by the decontamination agents.

Damage to natural flora and fauna caused by the decontaminant agent.

Damage to the crops caused by the decontaminant agent.

Cross-contamination, Spread of Infections and Waste Disposal from Hospitals, Clinics and Diagnostic Laboratories

Unsafe procedures in hospitals and laboratory can cause cross-contamination and/or spread of infections among the staff, patients and general public.  In addition, improper disposal of wastes from the facilities to be supported by the project may pose environmental and public health risks.  Specifically, the following risks are associated with the improper disposal of wastes from these facilities:

Health risk for the hospital/laboratory staff and people coming in contact with them.

Health risk for the personnel handling the wastes.

Contamination of soil and water.

Health risk for the nearby population.

Threat to wildlife particularly when such facilities are located outside major towns.

### Construction Activities

Construction activities as part of the AI project may contaminate air and water.  The following specific environmental impacts may be caused by these activities:

Air pollution caused by the exhaust from the vehicles and construction equipment.

Water contamination as a result of construction activities, repair of construction machinery/vehicles at site.

Inappropriate disposal of construction waste may cause soil and water contamination, as well as public nuisance.

Noise from the construction activities may be a source of nuisance to the nearby people (patients, staff, nearby population, etc.)

Safety hazard for the project staff, clinic/hospital staff, patients, visitors and others.

## Mitigation Measures

The mitigation measures to forestall or reduce the adverse environmental and public health risks discussed above, are tabulated in Attachment 4.3 and discussed below.

### Transportation of Viral Agents by Surveillance Teams

To mitigate the potential risks and adverse impacts associated with the surveillance activities, the following measures will become the integral part of the project activities:

Development and implementation of the procedures and guidelines for safe handling of poultry birds and their products, wastes, etc.

Development and implementation of the procedures and guidelines for safe handling of wild birds.

Coordination with NEPA and forest department for surveillance of wild birds.

Provision and use of PPEs for the surveillance teams

Trainings to the surveillance teams on the safe procedures, use of PPEs, environmental aspects and mitigation measures.

Awareness raising of the communities on identification of AI and safe handling procedures.

### Handling, Culling and Transport of Infected and At-risk Birds

To mitigate the potential risks and adverse impacts associated with the culling activities, the following measures will become the integral part of the project activities:

Development and implementation of the procedures and guidelines for safe culling of poultry birds.

Development and implementation of the procedures and guidelines for safe culling of wild birds.

Coordination with NEPA and forest department for culling of wild birds, particularly in protected areas.

Provision and use of PPEs for the culling teams.

Trainings to the culling teams on the safe culling procedures, use of PPEs, environmental aspects and mitigation measures.

Awareness raising of the communities on the importance of culling, safe procedures, bio-security and precautionary measures.

### Disposal of Carcasses

To mitigate the potential risks and adverse impacts associated with the carcass disposal, the following measures will become the integral part of the project activities:

Development and implementation of the procedures and guidelines for selection of appropriate site for the burial pit.  The criteria for site selection will include aspects such as the following:

In consultation with the community

outside the community,

outside cultivation fields,

without blocking any existing routes

at a safe distance from any groundwater well/water stream/water channel,

avoiding natural path of rainwater drainage,

away from any places of historical, cultural, archeological or religious significance

away from wetlands

no damage to trees or any other flora of significance.

Development and implementation of the procedures for adequate and safe backfilling of the burial pits.

Provision and use of PPEs during the burial operation.

Trainings to the burial teams on the safe burial procedures, use of PPEs, environmental aspects and mitigation measures.

Awareness raising of the communities on the importance of safe burial and precautionary measures.

Coordination with NEPA and forest department for burial of wild birds, particularly in forests, protected areas or near wetlands.

### Decontamination

To mitigate the potential risks and adverse impacts associated with the decontamination of the infected areas, the following measures will become the integral part of the project activities:

Development and implementation of the procedures and guidelines for decontamination.

Provision and use of PPEs during the decontamination operation.

Trainings to the field teams on the safe contamination procedures, use of PPEs, environmental aspects and mitigation measures.

Awareness raising of the communities on the importance of decontamination and precautionary measures.

Cross-contamination, Spread of Infections, and Waste Disposal from Hospitals, Clinics and Diagnostic Laboratories

The following measures will ensure that the waste disposal from the hospitals, clinics and laboratories do not cause significant environmental and/or public health risks:

Implementation of bio-safety level standards in the laboratories.

Implementation of standard safety procedures and use of PPEs, in order to avoid cross-contamination and spread of infections from the hospitals and laboratories.

Development and implementation of the procedures and guidelines for segregation, handling and disposal of wastes from hospitals, clinics and laboratories supported by the project.

Appropriate design of disposal wells.

Provision and use of PPEs during the waste handling and disposal.

Training of hospitals and laboratory staff on bio-safety level standards and safe practices.

Trainings to the waste disposal teams on the safe waste handling procedures, use of PPEs, environmental aspects and mitigation measures.

Awareness raising of the other staff on the importance of safe waste disposal.

### Construction Activities

In order to mitigate the environmental impacts that may be caused by the construction activities, the following mitigation and control measures will be enforced:

The standard good construction practices will be implemented.  In particular, the following steps/measures will be undertaken:

The construction machinery and vehicles will be kept in good working condition, avoiding excessive exhaust emissions.

Waste effluents (such as used oils) and contaminated water will not be released to the environment.

Construction waste will be disposed appropriately.

Excess construction material and scrap will not be left at the construction site.

Noise emissions will be minimized through appropriate means (using equipment in good working condition and having silencers, using sound barriers, if needed, etc.)

Safety hazard for the construction crew and the hospital/lab staff will be minimized through appropriate safety procedures, use of PPEs, and restricting unauthorized entry into the construction area.

Environmental training to the construction staff/crew on good construction practices, waste disposal, safety aspects and public nuisance.

## Residual Environmental Impacts

With the help of the mitigation and control measures discussed in Section 4.3 above, the adverse environmental impacts and health risks will be minimized to safe levels.  Attachment 4.4 presents the residual impacts of the project activities.

Attachment 4.1:  Screening Matrix (Un-mitigated)

|  | Physical | Biological | Social and Socioeconomic |
| --- | --- | --- | --- |
|  | Soil Erosion / Contamination | Air Quality | Surface Water Quality | Groundwater Quality | Water Availability and Consumption | Natural Vegetation | Wildlife | Land Acquisition | Agriculture / Poultry | Blocked Access | Noise and Vibration | Safety Hazard | Employment/Earning Opportunities | Infrastructure | Public Health (Health hazard for project staff and communities) | Aesthetic Value | Sites of Archeological, Historical or Cultural Significance - | Impacts on Indigenous People |
| Disease Surveillance | -2 | -1 | -2 | 0 | N | N | -2 | N | -2 | N | N | N | N | N | -2 | N | N | N |
| Culling and Associated Activities | -2 | -1 | -2 | -1 | N | N | -2 | N | -2 | N | N | N | +1 | N | -2 | N | N | N |
| Carcass Disposal | -2 | -1 | -2 | -2 | N | -1 | -2 | 0 | -2 | -1 | 0 | -1 | +1 | N | -2 | N | -1 | N |
| Decontamination | -2 | -1 | -2 | -1 | N | -1 | -1 | N | -1 | N | N | N | N | N | -2 | N | N | N |
| Cross-Contamination, Spread of Infections and Waste Disposal from Hospitals and Laboratories | -2 | 0 | -2 | -2 | N | 0 | -1 | 0 | 0 | 0 | N | -1 | N | N | -2 | N | N | N |
| Construction Activities | -1 | -1 | -2 | -1 | -1 | 0 | 0 | N | N | 0 | -1 | -1 | +1 | 0 | -2 | -1 | N | N |

Key:  -2:  High negative impact;  -1: Low negative impact;  0:  insignificant/negligible impact;  +1: low positive impact; +2: High positive impact, N: no impact.

Attachment 4.2:  Comparison of Disposal Methods for Animal Wastes Generated from Avian Influenza Outbreaks

| Description | Environmental considerations | Safety considerations | Advantages/ Disadvantages |
| --- | --- | --- | --- |
| Option 1: Burial in a Pit |
| Decomposition of dead birds/ carcasses and other wastes through biological degradation in a pit and involves: Excavation of a burial pit. Placing carcasses in a deep burial pit. Covering carcasses and other wastes with soil (about 40 cm) to: (a) prevent carcasses from rising out of the pit; (b) prevent scavengers digging up carcasses; (c) help filter out odors; and (d) absorb the fluids of decomposition. Adding an unbroken layer of slaked lime [Ca(OH)2] to protect carcasses from being uncovered by carnivores and earthworms after pit closure (lime should not be placed directly on carcasses because in wet conditions it slows, and may prevent, decomposition). Closing the pit to ground level with soil (at least 2 meters of soil is required in total). | Site Selection Considerations: Distance to watercourses, bores, and dug wells. Height of water table (the base of the pit must be well above the water table). Slope of the land at the burial site to the nearest watercourse (drainage to and from the pit). Soil permeability. Distance to human settlements and public lands (including roads). Prevailing wind direction (for odor emission). Availability of space for temporary storage of excavated soil. Accessibility of the burial site by digging equipment (e.g., excavator). Burial Site Inspection: Three (3) months after closure, inspection of the burial site to identify any potential problems (e.g., seepage) and take corrective measures. Transportation-Related Waste/Wastewater Treatment: Any wastewater generated from cleaning/disinfection of vehicles/ containers should be disinfected before discharge. Any waste generated during loading and unloading of vehicles as well as cleaning/disinfection of vehicles/containers should be safely disposed. | Use of personal protection equipment (PPE) to ensure hygiene and safety of personnel working at the site. Availability of emergency response measures and equipment for safety breaches (e.g., availability of first aid and rescue equipment if the personnel falls into the pit). Established and documented cleaning/disinfection procedures. Availability of cleaning/ disinfection supplies/equipment. Personnel training on personnel hygiene and safety measures. Transportation of Carcasses/Wastes to an Environmentally Suitable Site: If carcasses and other contaminated materials need to be transported off-site for disposal, then: The vehicles must be leak-proof and covered. The vehicles and external surfaces of containers should not leave the culling area without first being thoroughly cleaned/ disinfected. The vehicles and internal, external surfaces of containers should be cleaned/ disinfected after unloading carcasses and other wastes at the environmentally suitable site. | Advantages: Safe disposal if environmental conditions are met. Risk of disseminating the virus to other sites can be avoided if burial can be done on site. Low cost. Disadvantages: Likely to be affected by surface water, groundwater, soil or topographical conditions. If transportation to an environmentally suitable site is required, then: (a) increases the risk of disseminating the virus to other sites, and (b) higher costs for transportation and associated mitigation measures. Risk of groundwater contamination if site selection is not appropriate. |
| Option 2: Open Air Burning (Cremation) |
| This method is based on destruction of infective pathogens, animal carcasses and other wastes through thermal destruction in open air. It involves: Digging trenches, which act as air vents. Placing pyre (wood) on top of trenches (upwind, at right angle to the prevailing wind direction). Placing carcasses and other wastes at the opposite side. Pouring fuel (e.g., kerosene) onto carcasses, other wastes and pyre and starting fire (adequate supply of fuel must be at the site to ensure complete cremation). | Site Selection Considerations: Potential adverse impacts of heat, smoke or odor on nearby people, infrastructure (structures, underground and aerial utilities, roads, etc.) and environment (e.g., trees). Accessibility of equipment to construct and maintain the fire and for delivery of fuel and carcasses The ashes should be buried and the site should be restored. Waste Pretreatment/Containment: To avoid emission of dioxins or furans during cremation, carcasses should not be pretreated with a chlorine-bearing disinfectant or should not be contained in PVC bags. For the same reason, no other material destined for cremation should contain chlorine-bearing chemicals. | Maintaining adequate fire break around the pyre (consult local fire brigades or residents for advice). Use of PPE to ensure hygiene of personnel working at the site. Availability of emergency response measures and equipment for safety breaches (e.g., availability of first aid equipment and availability of fire fighting equipment and personnel if fire spreads around). Established and documented cleaning/disinfection procedures. Availability of cleaning/ disinfection supplies/equipment. Personnel training on personnel hygiene and safety measures. | Advantages: Cremation is not affected by surface water, groundwater, soil, and topographical conditions. Low cost, compared to incinerator option. Disadvantages: Infective pathogens may not be effectively destroyed if combustion of carcasses and wastes is incomplete, especially under adverse atmospheric conditions (wind, precipitation). It is not possible to easily verify that all infective pathogens are destroyed in the incomplete combustion process. Air emissions from open air burning (PM, CO2). Disposal of ash from cremation requires consideration for surface water, groundwater, soil and topographical conditions. More expensive than option 1 (burial). |
| Option 3: Composting |
| This method is based on thermal deactivation of the virus and decomposition of carcasses, litter and other contaminated organic wastes through aerobic biological degradation. Success of composting depends on: (a) proper nutrient mix; (b) moisture; (c) temperature; and (d) pH. Details can be found in technical documentation and websites listed. | Site Selection Considerations: Must be done at the affected farm in a secure area not accessible by other animals (such as birds, rodents, cats, or dogs). Proximity to residential areas and water sources (must be away). | Use of PPE to ensure hygiene of personnel working at the site. Availability of emergency response measures and equipment for safety breaches. Established and documented cleaning/disinfection procedures. Availability of cleaning/ disinfection supplies/equipment. Personnel training on personnel hygiene and safety measures. | Advantages: Effective for manure and litter waste. Can be undertaken within sheds or otherwise on site to avoid the risks of disseminating the virus through transport. No transportation cost. Disadvantages: Maintaining optimum temperatures for many days in cold climate areas/seasons may not be possible (or may be costly). Infective pathogens may not be effectively destroyed if ideal conditions are not achieved. Risk of disseminating the virus if the composting area is not effectively secured/isolated. It may not be possible to easily verify that all infective pathogens are destroyed. |
| Option 5: Incineration (Fixed) |
| This method is based on thermal destruction of infective pathogens, carcasses and other wastes in an incinerator. It involves: Transporting carcasses and other wastes to the incineration site. Cleaning containers and vehicles transporting carcasses and wastes, with treatment of the resulting wastewaters. Incinerating carcasses and other wastes (using fuel and air) at a high temperature. Transporting incineration residues (bottom ash/slag and fly ash) to the disposal site and disposal at the sanitary landfill. | Site Selection Considerations: Should not be in a floodplain. Distance to human settlements. Human settlements upwind of the prevailing wind direction (for odors before incineration and emissions from incineration). Technology Requirements: Incinerator at a minimum temperature of 850oC and with a minimum residence time of 2 seconds. Temperature must be measured and recorded. Incinerator equipped with an auxiliary burner that can be switched on when the temperature falls below 850oC. Incinerator automatic feed system connected to temperature measurement. Site security and inaccessibility by animals (such as birds, rodents, insects and other vermin). Storage areas for animal carcasses and other wastes as well as incineration residues must be covered. These areas must be labeled and designed and operated to prevent accidental releases of polluting substances to the environment. Storage capacity provided to collect contaminated storm water and wastewater from spillage or firefighting. Transportation of bottom ash/slag and fly ash in closed containers to prevent environmental releases. Disposal of bottom ash/slag and fly ash in a sanitary landfill. Waste Pretreatment/Containment: To avoid emission of dioxins or furans during incineration, carcasses should not be pretreated with a chlorine-bearing disinfectant or should not be contained in PVC bags. For the same reason, no other material destined for incineration should contain chlorine-bearing chemicals. | Use of PPE to ensure hygiene of personnel working at the site (incinerator operators must change their PPE before handling animal carcasses and other wastes). Established and documented cleaning/disinfection procedures. Established and documented emergency response procedures. Availability of cleaning/ disinfection supplies/equipment. Availability of emergency response equipment (e.g., first aid, fire fighting) Personnel training on personnel hygiene/cleaning, safety and emergency response measures. Regular inspections of the environment and equipment, with documented inspection schedules and results. Transportation of Carcasses/Wastes to the Incineration Site: When carcasses and other contaminated materials are transported to the fixed incineration site, then: The vehicles must be leak-proof and covered; The vehicles and the external surfaces of containers should not leave the culling area without first being thoroughly cleaned/disinfected; and The vehicles and internal/external surfaces of containers should be cleaned/ disinfected after unloading carcasses and other wastes at the incineration site. Transportation of Incineration Residues to the Disposal Site: The vehicles must be covered. The vehicles and containers should not leave the incineration area without first being thoroughly disinfected. | Advantages: Complete destruction of infective pathogens. Over 95% waste reduction. Disadvantages: Complex technology which may be imported to the country. High investment cost. High operating cost (especially fuel cost). Some spare parts may need to be imported (cost and downtime of incinerator in case of AI outbreak). High level of operator training. Scrutinized administrative requirements (recordkeeping, etc.). The incineration facility may be too far from the location with the AI outbreak, requiring extensive transportation of carcasses and other wastes with infective pathogens, resulting in: (a) increased risks of disseminating the virus to other sites; and (b) higher costs for transportation and associated mitigation measures. Air emissions from the incinerator (PM, SO2, CO2). |
| Option 6: Incineration (Mobile) |
| This method is based on thermal destruction of infective pathogens, animal carcasses and other wastes in an incinerator. It involves: Transporting the mobile incinerator to the culling site. Incinerating carcasses and other wastes (using fuel and air) at a high temperature. Transporting incineration residues (bottom ash/slag and fly ash) to the disposal site and disposal at the sanitary landfill. | Technology Requirements: Incinerator at a minimum temperature of 850oC and with a minimum residence time of 2 seconds. Temperature must be measured and recorded. Incinerator equipped with an auxiliary burner that can be switched on when the temperature falls below 850oC Incinerator automatic feed system connected to temperature measurement. Storage areas for animal carcasses and other wastes as well as incineration residues must be covered. These areas must be ventilated, labeled, and designed and operated to prevent accidental releases of polluting substances to the environment. Transportation of bottom ash/slag and fly ash in closed containers to prevent environmental releases. Disposal of bottom ash/slag and fly ash in a sanitary landfill. Waste Pretreatment/Containment: To avoid emission of dioxins or furans during incineration, carcasses should not be pretreated with a chlorine-bearing disinfectant or should not be contained in PVC bags. For the same reason, no other material destined for incineration should contain chlorine-bearing chemicals. | Use of PPE to ensure hygiene of personnel working at the site (incinerator operators must change their PPE before handling animal carcasses and other wastes). Established and documented cleaning/disinfection procedures. Established and documented emergency response procedures. Availability of cleaning/ disinfection supplies/equipment. Availability of emergency response equipment (e.g., first aid, fire fighting) Personnel training on personnel hygiene/cleaning, safety and emergency response measures. | Advantages: Complete destruction of infective pathogens. Over 95% waste reduction. Avoids the need to transport the infective pathogens, carcasses, and other wastes to the incinerator (i.e., reduced risk of disseminating the virus to other sites compared to the fixed incineration case). Disadvantages: Complex technology which may be imported to the country. High investment cost and high operating cost. Some spare parts may need to be imported (cost and downtime of incinerator in case of AI outbreak). High level of operator training. Scrutinized administrative requirements (recordkeeping, etc.). Transportation of the mobile incinerator to the culling site is associated with: (a) the risk of exposing the incinerator (i.e., the investment) to damage/total loss in case of an accident (contributed by poor road conditions, severe weather, etc.); and (b) high cost of transporting incinerator to the culling site. Accessibility of the culling site by the mobile incinerator. Air emissions from the incinerator (PM, SO2, CO2). |

Attachment 4.3:  Mitigation and Monitoring Plan

| Project Activities | Potential Major Impacts/issues | Mitigation Measures | Monitoring Requirements | Responsibility for Mitigation | Responsibility for Monitoring |
| --- | --- | --- | --- | --- | --- |
| Animal Health Component |  |  |  |  |
| Strengthening Animal Disease Surveillance and Diagnostic Capacity | Transport of viral agents by surveillance teams and vehicles. | Follow appropriate safety procedures and guidelines during disease surveillance. Use of PPE. Disinfection of personnel, equipment and vehicles after surveillance in infected/at risk areas. | Availability of appropriate safety procedures and guidelines during disease surveillance. Staff trainings in safety procedures and guidelines. Presence and use of PPE. Availability and use of disinfectants. | Surveillance teams. | Zonal M&E coordinator; EFP (AH) |
|  | Laboratory cross-contamination or infections caused by viral agents. Poor management of lab waste. | Follow appropriate Bio-safety Level Standards by supporting upgrading of labs and training of staff. Follow internationally accepted lab waste management practices. (EWMS will develop waste disposal guidelines, based upon the international best practice and the local conditions.) | Inspection of premises, staff training and introduction of safety procedures, diagnostic labs, prior to installation of equipment and at six month intervals thereafter. | Laboratory staff through its incharge | Zonal M&E coordinator; EFP (AH) |
| Collection and disposal of infected and dead birds | Poses risks of spreading the virus and of exposure of personnel. Impacts to residents, particularly children, bringing dead birds to personnel collecting the birds. | Policy and operating procedures, manual for collecting infected and dead wild birds and domestic birds for sampling purposes. (Detailed waste disposal guidelines will be developed by EWMS during the first three months of the project.) Public education and warnings for people bringing infected and dead birds to collectors and disinfection procedures. Use personnel protective equipment (PPE), HazMat and decontamination procedures as for culling, described below. | During regular supervision, verify availability and use of PPE and certification of personnel. Monitor health status/record of personnel involved in collection/transport/ disposal. | ERTs | Zonal M&E Coordinator; EFP (AH) during occasional field visits. |
| Culling of birds | Impacts to residents, particularly children, bringing dead birds to personnel collecting the birds. Poses risks of spreading the virus and of exposure of personnel. Risks of intoxication when using chemicals for culling. Risk of heat stress and fatigue from working in PPE. Distress to residents and farmers observing on-site culling of their birds. Risk to casual onlookers entering the culling or decontamination zone. | Public education and warnings for people bringing infected and dead birds to collectors and disinfection procedures. Follow OIE/FAO, WHO, NABCC, AusVet, and other relevant guidelines on culling. Use PPE, HazMat work zone concepts, buddy system, rest breaks, and decontamination procedures, as in OSHA, AusVet, NABCC and OIE/FAO guidelines. Code of conduct on distribution, handling and use of culling chemicals, as well as pesticides to control vectors during any storage or transport prior to final disposal. Provide all residents and farmers with detailed information explaining the HPAI threat and the need for culling. Provide counseling for distressed people, including children, observing culling and experiencing loss of their household pets and domestic birds. | Verify guidelines in OM and Procurement documents for disposable and cleanable PPE gear to include full body cover, impermeable apron, gloves, eye goggles, fine particle mask for virus, ear plugs, boots or shoe covers, and duct tape. Enough sets for decontamination and clean suiting for at least 3 breaks/day. Training manuals and training. On-site health and safety plan. On-site certified supervision. Vaccination of culling workers. Monitor health status/record of culling workers Enforcement of an exclusion and transition zone for culling and decontamination of workers and equipment. | ERTs | Zonal M&E Coordinator; EFP (AH) during occasional field visits. |
| Transport of infective materials and dead birds | Pose risks of spreading the virus and of exposure of personnel | Collection and transport in closed containers that do not leak or release air emissions. Only use trained and certified personnel that have access to and use the recommended protective gear. Only use personnel that have been vaccinated. | Follow a manifest system to record source to endpoint transport, as in HazMat procedures. Verify availability and use of PPE and certification of supervision personnel. Monitor health status/record of personnel involved in collection and transport. | ERTs | Zonal M&E Coordinator; EFP (AH) during occasional field visits. |
| Disposal of culled Birds | Poor choice of disposal options and disposal sites may pose risk to spreading the virus, or cause water or air contamination. Risk of toxicity when handling pesticides to control vectors during work or carcass storage. Risk of heat stress and fatigue from working in PPE. | Follow waste disposal guidelines (EWMS will develop the detailed waste disposal guidelines, with the help of OIE/FAO, WHO, NABCC, AusVet, and other relevant guidelines). Use PPE, HazMat work zone concepts, buddy system, rest breaks, and decontamination procedures, as in OSHA, AusVet, NABCC and OIE/FAO guidelines. | During regular supervision, confirm whether environmental and safety considerations are met; Verify certification of personnel; availability and use of PPE and hazmat procedures, including decontamination of workers and vehicles. | ERTs | Zonal M&E Coordinator; EFP (AH) during occasional field visits. |
| Disposal of farm waste (manure, eggs, feathers, contaminated equipment, disposable PPE, etc.). | Risk of dissemination of the virus during movement and transport of manure, litter, bedding, feathers, etc.. Risk of dissemination of virus when handling contaminated eggs and hatchery waste and/or equipment, or reusing egg cartons and cages. Risk of water pollution and bioaerosols. | Follow waste disposal guidelines (EWMS will develop the detailed waste disposal guidelines, with the help of OIE/FAO, WHO, NABCC, AusVet, and other relevant guidelines). Use PPE, HazMat work zone concepts, and decontamination procedures, as in OSHA, AusVet, NABCC and OIE/FAO guidelines. | During regular supervision, confirm whether environmental and safety considerations are met; Verify certification of personnel; availability and use of PPE and hazmat procedures, including decontamination of workers and vehicles. | ERTs | Zonal M&E Coordinator; EFP (AH) during occasional field visits. |
| Decontamination | Risk of virus dissemination. Risk of groundwater and surface water pollution. Risk of intoxication and chemical burns when using chemicals. | Use FAO, OIE and WHO recommended detergents and disinfectants for HPAI. (See footnote above for culling) Thoroughly disinfect materials and surfaces that came in contact with bird droppings, blood or other contaminated materials. Disinfect workers, equipment and vehicles that leave the exclusion work zone, as well as vehicle tires as they leave the eradication area. | Procurement of recommended disinfectants and detergents, wash tubs, decontamination catchment tubs, portable showers, ground covers, long-handled brushes, etc. Verify procedures and training manuals address HPAI-specific recommendations. Clean PPE for use after each break where decontamination procedures must be followed, including smoking or water breaks. | ERTs | Zonal M&E Coordinator; EFP (AH) during occasional field visits. |
| Human Health Component |  |  |  |  |
| Improvements of Laboratory Networks | Cross-contamination or infections caused by viral agents. Poor management of lab waste. | Follow appropriate Biosafety Level Standards by supporting upgrading of labs and training of staff. Follow internationally accepted lab waste management practices. (The EWMS will develop waste disposal guidelines.) | Inspection of premises, staff training and introduction of safety procedures at all diagnostic labs, prior to installation of equipment and at six month intervals thereafter. | Laboratory personnel | Zonal M&E coordinator; EFP (HH) |
| Medical Services (includes support to rehabilitate and equip selected health facilities for the delivery of critical medical services) | Cross-contamination or infections caused by viral agents due to poor management of: infectious health care wastes; and laboratory wastes. | Follow the hospital/health clinic specific comprehensive laboratory waste management and health care waste management plans. (The EWMS will develop waste disposal guidelines.) | Inspection of premises, staff training and introduction of safety procedures at all medical facilities supported by the project, prior to installation of equipment and at six month intervals thereafter. | Hospital staff | Zonal M&E coordinator; EFP (HH) |
|  | Construction related impacts. | Any potential adverse impacts arising out of the limited civil works (during the construction period) will be addressed by following standard good construction practices/FIDIC standards. | Regular supervision of construction activities will include monitoring the implementation of FIDIC standards. | Contractor’s staff | Zonal M&E coordinator; EFP (HH) |

Attachment 4.4:  Residual Impacts

|  | Physical | Biological | Social and Socioeconomic |
| --- | --- | --- | --- |
|  | Soil Erosion / Contamination | Air Quality | Surface Water Quality | Groundwater Quality | Water Availability and Consumption | Natural Vegetation | Wildlife | Land Acquisition | Agriculture / Poultry | Blocked Access | Noise and Vibration | Safety Hazard | Employment/Earning Opportunities | Infrastructure | Public Health (Health hazard for project staff and communities) | Aesthetic Value | Sites of Archeological, Historical or Cultural Significance - | Impacts on Indigenous People |
| Disease Surveillance | 0 | 0 | 0 | 0 | N | N | 0 | N | 0 | N | N | N | N | N | 0 | N | N | N |
| Culling and Associated Activities | 0 | 0 | 0 | 0 | N | N | -1 | N | -1 | N | N | N | +1 | N | -1 | N | N | N |
| Carcass Disposal | 0 | 0 | 0 | -1 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | +1 | N | -1 | N | 0 | N |
| Decontamination | 0 | 0 | 0 | 0 | N | 0 | 0 | N | 0 | N | N | N | N | N | -1 | N | N | N |
| Cross-Contamination, Spread of Infections and Waste Disposal from Hospitals and Laboratories | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | N | 0 | N | N | -1 | N | N | N |
| Construction Activities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | N | 0 | -1 | -1 | +1 | 0 | -1 | 0 | N | N |

Key:  -2:  High negative impact;  -1: Low negative impact;  0:  insignificant/negligible impact;  +1: low positive impact; +2: High positive impact, N: no impact.

# Institutional and Implementation Mechanism

This section describes the institutional and implementation arrangements devised for the AI project.

## Institutional Arrangements

The ultimate responsibility of the environmental performance of the project rests with the implementing ministries (ie, MAIL and MOPH) for their respective components of the AI project.  The ministries will fulfill their responsibilities through the project coordinator, who will be assisted by the animal health coordinator, human health coordinator, M&E specialist and environmental and waste management specialist (EWMS).

The project staff, contractor and other relevant staff from the project supported facilities will be responsible for the implementation of the mitigation measures, as tabulated in Attachment 4.3.

#### Roles and Responsibilities

Roles and responsibilities of the key project personnel for the environmental management of the project are discussed below and tabulated in Attachment 5.1.

EWMS:  The EWMS will operationalize the environmental management plan.  The EWMS will also implement the environmental training plan.  S/he will also be responsible for developing detailed waste disposal guidelines for carcass disposal and wastes from hospitals, clinics and laboratories supported by the project.  The EWMS’s ToR is provided in Attachment 5.2.

The EWMS will be available to the project for a total duration of 6 months.  During the initial 2-3 months, s/he will carry out the following specific tasks:

Operationalize the EMP,

fulfill the regulatory requirements,

finalize the environmental monitoring framework in close coordination with the M&E specialist,

design and conduct environmental trainings,

develop waste disposal guidelines,

ensure that the EMP and waste disposal guidelines are translated in Dari and Pashto.

After the initial inputs stated above, the EWMS will be available to the project during brief missions, during which s/he will:

review the implementation status of the mitigation measures,

study the environmental monitoring reports,

evaluate the effectiveness of environmental monitoring,

identify/recommend ‘course corrections’ if warranted on the basis of the field observations, results of the environmental monitoring, and/or inputs from other agencies (such as NEPA),

conduct additional environmental trainings, if needed.

Field teams:  The EMP defines the mitigation measures however, implementation of these measures will be the responsibility of the field teams, as given below:

ERTs for the mitigation measures associated with culling and carcass disposal,

surveillance teams for the control measures during disease surveillance, and

hospitals’ and clinics’ waste disposal staff for implementing the waste disposal guidelines,

construction contractors for mitigation measures associated with the construction activities.

Zonal M&E Coordinators:  The zonal M&E coordinators will be responsible for carrying out the environmental monitoring in the field.  They will ensure that the field teams (surveillance teams, ERTs and others) effectively implement the mitigation measures identified in the mitigation plan (Attachment 4.3).  They will fill simple checklists and forms (provided to them by the M&E specialist/EWMS), and send these to the M&E specialist in Kabul.  The zonal coordinators will receive trainings for these aspects.  The EWMS and EFPs (discussed below) will provide technical support and backstopping to the zonal M&E coordinators.

M&E Specialist:  The M&E specialist will be responsible to implement the environmental monitoring framework designed by the EWMS.  As described above, the environmental monitoring in the field will be carried out by the zonal M&E coordinators, who will send the monitoring data to the M&E specialist.  Based upon the data received from the regional teams, the M&E specialist will produce regular environmental monitoring reports.  The EFPs (discussed below) will assist the M&E specialist in preparing and reviewing these reports.

Environmental Focal Points (EFPs):  Both MAIL and MOPH will have their respective EFPs, who will assist EWMS in:

operationalizing the EMP,

conducting stakeholder consultations, and

implementing environmental trainings.

They will also support M&E specialist and zonal M&E coordinators for environmental monitoring of the project activities for their respective area of responsibility in the project (particularly during the absence of EWMS).  They will also be required to conduct field visits, to ensure effective implementation of the mitigation measures and monitoring framework.

The ToRs for the EFPs are provided in Attachments 5.3 and 5.4.  The EWMS will be responsible to train the EFPs, in addition to providing technical support and backstopping.

## Implementation Arrangements

The environmental management of the AI project will be carried out with the help of the following key activities:

- Public disclosure and stakeholder consultations

- EMP operationalization

- Fulfilling requirements arising from national legislation

- Development of waste disposal guidelines

- Environmental trainings

- Implementation of the mitigation measures

- Environmental monitoring

- Documentation and reporting.

The first four activities of the above list are discussed below, while the remaining are discussed in separate chapters later in this document.

### Public Disclosure and Stakeholder Consultations

Stakeholder consultation will continue throughout the project duration.  It started during the project development stage, and continued during the EMP adaptation and development of the present document (POM).

Further consultations will be conducted in order to disseminate salient features of the project and EMP, and also for obtaining views, concerns and apprehensions of the stakeholders.  These consultations will be carried out with NEPA, UNEP, implementing ministries (MAIL and MOPH), zonal/regional officials and relevant NGOs.  Consultations will also be carried out with selected communities.  Consultation workshops will be held in Kabul and other zones (where project’s zonal coordinators are present) for this purpose.

EWMS will be responsible for this task, with assistance from the EFPs and zonal coordinators.

Subsequent to the above, consultations with the key stakeholders will continue throughout the project, primarily during meetings with NEPA, environmental monitoring and visits of EWMS and EFPs to the field.

### EMP Operationalization

A generic EMP existed as part of the project documents (Technical Annex), which has been adapted and expanded making it more specific for the project as well as the local conditions in Afghanistan.  During the early stages of the project implementation, the EMP will be further elaborated and operationalized.  This will be carried out on the basis of the stakeholder consultations discussed above, and the key inputs provided by the M&E specialist.  The guidance and advice from NEPA will also be sought for this purpose.

The key steps in operationalizing the EMP will include:

Review of the outcome of the stakeholder consultations (discussed in Section 5.2.1 above),

Discussions with the M&E specialist, and if needed with the zonal M&E coordinators, on the environmental monitoring framework,

Finalization of the environmental indicators to be monitored

Need identification for the environmental trainings

Finalization of environmental training plan

Review of EMPs from other countries, preferably for the AI projects

Detailed discussions and consultations with NEPA, in order to obtain their guidance and advice.

The EWMS will be responsible for this activity, with assistance from the EFPs.

Once operationalized, the EMP will be translated in Dari and Pashto (MAIL to be responsible for the translation).  Subsequently it will be made available to the key stakeholders in all zones for their review and feedback.

### Fulfilling Requirements Arising from National Legislation

The Afghanistan’s environmental protection act requires that the project proponents conduct environmental assessments and submit its report to NEPA for review and approval.  In line with this requirement, the EMP will be submitted to NEPA.

The EWMS will also review other environmental regulations which are in the process of being developed/enforced.  In response to these regulations and in consultation with NEPA and UNEP (which provides technical support to NEPA), EWMS will identify any further action to be taken by the project.

### Development of Waste Disposal Guidelines

The EWMS will be responsible to develop the waste disposal guidelines for various project activities.  Three distinct sets of waste disposal guidelines are expected to be developed:

Waste resulting from birds culling and associated activities,

Wastes generated from hospitals, clinics and laboratories (supported by the project),

Waste generated during the construction activities.

The guidelines will provide the procedures for collecting, segregation (where applicable), handling and disposal of various types of wastes listed above.

The steps involved in developing the waste disposal guidelines include the following:

- Review of the project activities generating waste.

- Review of the international best practice for the disposal of each kind of waste.

- Review of the prevailing disposal practices in the developing countries in the region (India, Pakistan, Iran, Uzbekistan, Tajikistan and others).

- Review of the existing waste handling and disposal practices in the country.

- Identifying and evaluating various waste disposal options for each type of waste.

- Discussing the waste disposal options with the project team, the implementing ministries, NEPA and UNEP.

- Selecting the most appropriate disposal options (for each type of waste).

- Preparing detailed guidelines for the selected options.  As stated above, three set of guidelines will be developed for: i) waste generated by culling and associated activities; ii) waste generated from hospitals, clinics and laboratories; and iii) construction waste.

- Once finalized, the guidelines will be translated in Dari and Pashto (MAIL and MOPH to be responsible for their respective guidelines).

This task will be completed within first three months of the project initiation.

Most of these waste disposal guidelines – particularly the ones for hospital/laboratory waste and construction waste – will be applicable to other similar facilities/projects.

### Implementation Schedule

Attachment 5.5 provides the implementation schedule for the environmental management activities.

## Legal and Contractual Arrangements

The institutional and implementation arrangements discussed in Sections 5.1 and 5.2 above, have been made part of the project’s operational manual, hence making it a binding on the project team.  For the construction contractors, appropriate clauses will be included in their contracts so as to make complete implementation of the mitigation measures a contractual binding.

Attachment 5.1:  Roles and Responsibilities

|  | Schedule | Tasks | Notes |
| --- | --- | --- | --- |
| Environmental and Waste Management Specialist (EWMS) | During initial 3 months. | Conduct stakeholder consultation workshops. | Environmental Focal Points (EFPs) and zonal M&E coordinators to assist. |
|  |  | Finalize environmental monitoring framework, including environmental indicators/parameters to me monitored. | M&E specialist to assist. |
|  |  | Operationalize EMP. | EFPs to provide assistance. |
|  |  | Fulfill all regulatory requirements. |  |
|  |  | Develop waste disposal guidelines. | EFPs to provide assistance. |
|  |  | Develop environmental training modules. |  |
|  |  | Conduct environmental trainings. | EFPs to assist and participate in trainings. |
|  | After 3 months. | Review environmental monitoring reports and evaluate effectiveness. |  |
|  |  | Review implementation of mitigation measures through field visits. | EFPs to provide assistance. |
|  |  | Review overall environmental performance of the project activities. |  |
|  |  | Recommend course correction if needed. |  |
|  |  | Conduct additional environmental trainings (if needed). | EFPs to provide assistance. |
|  |  | Provide technical backstopping to EFPs and other project personnel. |  |
| Surveillance teams | Entire project duration | Implement the environmental mitigation and control measures for disease surveillance activities, as given in the mitigation plan (Attachment 4.3). | The surveillance teams will receive trainings to implement the mitigation measures. EFPs and EWMS to provide technical support and backstopping. |
| Culling and carcass disposal teams (ERTs) | Entire project duration | Implement the environmental mitigation and control measures for culling and carcass disposal activities, as given in the mitigation plan (Attachment 4.3). | The ERTs will receive trainings to implement the mitigation measures. EFPs and EWMS to provide technical support and backstopping. |
| Hospitals. Clinics and Laboratory staff | Entire project duration | Implementation of waste disposal guidelines. Implementation of bio-safety measures. | The staff will be provided trainings on the waste disposal and bio-safety guidelines. |
| Construction contractors | During construction activities | Implementation of environmental management and waste disposal procedures and mitigation measures, as given in the EMP. | The contractors’ relevant staff will be provided trainings on the waste disposal and bio-safety guidelines. |
| Zonal M&E Coordinators | Entire project duration | Monitor implementation of the mitigation measures as given in EMP. To regularly provide monitoring data (using the data format/checklists/forms provided by M&E specialist and EWMS) to M&E specialist. | The zonal coordinators will receive trainings on these aspects. EWMS and EFPs will provide technical support and backstopping. |
| M&E Specialist | First 3 months | Provide assistance to EWMS for developing environmental monitoring framework. |  |
|  | Entire project duration | Implement environmental monitoring framework. Prepare periodic monitoring reports on the basis of monitoring data provided by zonal M&E coordinators.. | EWMS and EFPs to assist M&E specialist in preparing monitoring reports. |
| EFPs | First 3 months | Assist EWMS in conducting stakeholder workshops. Assist EWMS in finalizing environmental monitoring framework. Assist EWMS in operationalizing EMP. Assist EWMS in developing waste disposal guidelines. Assist and participate in environmental trainings. | EFPs will receive trainings on these aspects. |
|  | After first 3 months | Assist M&E specialist and zonal M&E coordinators in environmental monitoring. Conduct field visits to culling and waste disposal sites, and laboratories (EFP-AH), to ensure implementation of mitigation measures. Conduct visits to hospitals and clinics (EFP-HH) to ensure implementation of mitigation measures. Conduct follow-up/refresher environmental trainings, if needed. Assist and support project staff on all matters regarding environmental management. | EWMS will provide technical support and backstopping. |

Attachment 5.2:  ToR for International Environmental and Waste Management Consultant

The International Consultant in close collaboration with the national focal points in MAIL and MOPH shall:

- Based on the Results Framework and Monitoring and the Environmental management Plan (EMP)– prepare a detailed M&E system, including data collection, tabulation, frequency of data collection, data analysis and evaluation, as well as reporting – to ensure that all minimum targets and objectives as well as the reporting objectives are fully achieved.

- Develop a detailed list of indicators with specifications of method of data collection, frequency and tabulation in a pre-designed database system.

- The system should be developed in close collaboration with the M&E Specialist.

- Provide specific reports to the WB as specified in the Results Framework and Monitoring as well as to NEPA and the project team.

- Assist the M&E Specialist in drafting the various reports, at least during the first year of the project implementation.

- Participating in focused group meetings and organized stakeholder workshops to understand the key areas of concern of different stakeholders, particularly vulnerable communities, private sector firms regarding the environmental and social impacts of the AI project activities;

- Assess through fieldwork the current status of applied personal safety, and waste and hazard materials management and disposal measures, with special emphasis on HPAI containment and control.

- Assessment of environmental training and capacity building needs in the relevant ministries;

- Plan, implement and monitor the environmental training of staff at various levels in the client ministries;

- Develop manuals and guidelines, applicable within the Afghan socio-economic context, on personal safety, and waste and hazard materials management and environmentally friendly disposal. Make sure that these materials are translated in the local languages and are available to relevant staff working on the project;

- Train trainers in the environmental aspects of culling operations, and laboratory personnel in personal safety measures and environmentally safe disposal of waste and hazard materials. Women trainers would be very needed to reach the women who raise backyard chickens to understand the bio-safety and issues and be able to benefit from the compensation when there is an outbreak and culling has to be undertaken.

- Identifying methodologies to establish and institutionalize the general waste management and hygienic practice in the relevant departments of the client ministries;

- Sharing international best practices and recommending actions for a more effective public awareness and public participation programs to prevent adverse environmental and social impacts of the program;

- Help mainstream environmental concerns into the policy formulation, program development and planning process.

Attachment 5.3:  ToR for Environmental Focal Point (Animal Health)

Under the direct supervision of the environmental and waste management specialist (EWMS) and in coordination with the project implementation team at the Ministry of Agriculture, Irrigation and Livestock (MAIL), the Environmental Focal Point (EFP) will perform the following functions:

- Maintain close liaison and coordination with the project implementation team in MAIL (particularly with the project coordinator, animal health coordinator and monitoring and evaluation coordinator).

- Participate and assist EWMS in focused group meetings and stakeholder workshops on the environmental and social impacts of the AI project activities.

- Assist EWMS in the management of environmental trainings of staff at various levels in the client ministry (MAIL), as well as participate in these trainings.

- Ensure effective environmental monitoring and data collection/reporting on environmental indicators (animal health component) by the field teams and regional monitoring and evaluation coordinators.  The environmental monitoring framework and data collection requirements will be provided in the environmental management plan (EMP) which will be prepared by the EWMS.

- Conduct occasional environmental monitoring visits to culling and burial sites in coordination with the emergency response teams responsible for these activities (culling and burial of carcasses).

- Review environmental monitoring reports (for animal health component) prepared by the regional monitoring and evaluation coordinators.

- Advise and assist project staff on all matters relating to environment and Environmental Management Plan implementation (animal health component), in consultation with/under the supervision of EWMS.

The EFP will be provided training(s) on the responsibilities listed above, and the Environmental Management Plan being developed for the project.

It is expected that the EFP will be available to the project on part time basis.  However the involvement and time requirement is likely to vary depending upon the project activities.

Attachment 5.4:  ToR for Environmental Focal Point (Human Health)

Under the direct supervision of the environmental and waste management specialist (EWMS) and in coordination with the Human Health Coordinator, the Environmental Focal Point (EFP) will perform the following functions:

- Maintain close liaison and coordination with the project implementation team in MAIL and MOPH (particularly with the project coordinator, human health coordinator and monitoring and evaluation coordinator).

- Participate and assist EWMS in focused group meetings and stakeholder workshops on the environmental and social impacts of the AI project activities.

- Assist EWMS in the management of environmental trainings of staff at various levels in the client ministry (MOPH), as well as participate in these trainings.

- Ensure effective environmental monitoring and data collection/reporting on environmental indicators (human health component) by the field teams and regional monitoring and evaluation coordinators.  The environmental monitoring framework and data collection requirements will be provided in the environmental management plan (EMP) which will be prepared by the EWMS.

- Ensure effective implementation and environmental monitoring of the hospital waste management system in the hospitals supported by the project.  The waste management system will be developed by the EWMS.

- Review environmental monitoring reports (human health components) prepared by the regional monitoring and evaluation coordinators.

- Advise and assist project staff on all matters relating to environment, waste management system and Environmental Management Plan implementation (human health components), in consultation with/under the supervision of EWMS.

The EFP will be provided training(s) on the responsibilities listed above, and the Environmental Management Plan being developed for the project.

It is expected that the EFP will be available to the project on part time basis.  However the involvement and time requirement is likely to vary depending upon the project activities.

Attachment 5.5:  Implementation Schedule

| Activities | Year 1 | Year 2 | Year 3 | Notes |
| --- | --- | --- | --- | --- |
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |
| Stakeholder consultations |  |  |  |  |  |  |  |  |  |  |  |  |  |
| EMP Operationalization |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Fulfilling NEPA requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development of waste disposal guidelines |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development of environmental training modules and initial trainings (ToT) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Follow-up trainings |  |  |  |  |  |  |  |  |  |  |  |  | Need based. |
| Implementation of the mitigation measures |  |  |  |  |  |  |  |  |  |  |  |  | According to the project activities (eg, culling, carcass disposal, etc.) |
| Environmental monitoring |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Documentation and reporting. |  |  |  |  |  |  |  |  |  |  |  |  |  |

# Environmental Monitoring

This section discusses the environmental monitoring that will be carried out during the AI project.

## Objective

The ultimate aim of the environmental monitoring is effective implementation of the EMP, and enhanced environmental performance of the project activities.  The objectives of environmental monitoring during the AI project are as follows:

Ensuring that the mitigation measures discussed in Section 4.3 are being implemented completely.

Ensuring the effectiveness of the mitigation measures in minimizing the project’s impacts on the environmental resources.

These objectives will be met through the implementation of the environmental monitoring framework discussed below.

## Environmental Monitoring Framework

The environmental monitoring framework consists of the following key elements:

Environmental monitoring parameters

Monitoring methodology

Monitoring forms and checklists

Monitoring tiers, roles and responsibilities

Environmental monitoring reports.

These elements are discussed below.

Monitoring Parameters:  The environmental monitoring parameters are tabulated in Attachment 4.3, against each project activities.

Methodology:  Mostly, the monitoring will be carried out through observation in the field.  A set of simple checklists will be developed on the basis of the monitoring plan (Attachment 4.3) during the initial phase of the project, which will be filled during the various field activities, such as surveillance, culling and carcass disposal.  The checklists will essentially record the field observations, including any non-compliances, during the environmental monitoring.  Through filling of these checklists, implementation of the mitigation measures will be ensured.  These checklists will be reinforced by photographs of the key activities/sites, such as culling and waste disposal.

Roles and Responsibilities, and Monitoring Tiers:  The overall responsibility of implementing the environmental management framework will rest with the M&E specialist.  The environmental monitoring will be carried out at three tiers, described below.

At the field level, the environmental monitoring will be carried out by the zonal M&E coordinators, who will fill the above-mentioned checklists during the field activities.  These filled checklists will be sent to the M&E specialist, who will maintain record of these checklists.

At the second level, the EWMS (when available to the project), EFPs and M&E specialist will conduct environmental monitoring during occasional field visits.  During these visits, they will observe the field activities and environmental monitoring conducted by the zonal M&E coordinators.  In addition, they will also look for any residual environmental impacts or unforeseen environmental aspect of the project activities.  This will ensure the effectiveness of the mitigation measures implemented during the field activities.

At the topmost tier, the periodic project supervisory missions from WB will monitor the field activities on a selective basis.

In addition to the above, monitoring teams from NEPA may also visit the project site in order to assess the environmental performance of the project.

Monitoring Reports:  The M&E specialist will prepare periodic environmental reports on the basis of the filled checklists received from the zonal M&E coordinators.  The EWMS and EFPs will provide assistance to him for this purpose.  These reports will provide information on the implementation of the mitigation measures, any non-compliances observed, and corrective actions recommended.

In addition to the above, a separate monitoring report will be prepared for each monitoring visit conducted by the EWMS, EFPs and/or M&E specialist.  These reports will document the field observations, implementation of the mitigation measures and monitoring requirements, any non-compliances observed or reported, any residual impacts observed, recommended corrective measures and any other relevant information.

Monitoring Framework Finalization:  The EWMS will finalize the environmental monitoring framework during the early phase of the project, with assistance from the M&E specialist.  During this phase, the monitoring checklists will be developed, environmental indicator (discussed below) finalized, formats of the monitoring reports prepared, and monitoring schedule framed.

## Monitoring Indicators

The environmental indicators help in effective environmental monitoring, evaluation and quantitative analysis of the environmental performance of the project.  An indicative list of the environmental indicators is provided below.

Number of non-compliances during each field operation (eg, culling of infected birds)

Number of environmental trainings conducted.

Number of project staff who received environmental trainings.

Number of monitoring visits conducted by EWMS, EFPs and M&E specialist.

Number of grievances received (eg, regarding compensation payment).

Number of grievances addressed satisfactorily.

Distance of the carcass disposal site from any existing ground water well.

Distance of the carcass disposal site from village/settlement.

Distance of the carcass disposal site from water course, water channel.

Distance of the carcass disposal site from any wetland.

Water table depth at/near the carcass disposal site.

Number of trees cut for the carcass disposal pit.

These indicators will be finalized by the EWMS in coordination with M&E specialist, during the early phase of the project.

# Environmental Trainings and Awareness Raising

This section provides the environmental training plan for the AI project.  Also discussed in the section is the planned process for environmental awareness raising.

## Objectives

The ultimate aim of the environmental trainings is effective implementation of the EMP, and enhanced environmental performance of the project activities.  The specific objectives of environmental trainings are as follows:

To enhance the environmental awareness among the project staff and other relevant personnel from the implementing ministries.

To build capacity of field teams, EFPs, zonal M&E coordinators and other project staff for their respective roles in environmental management.

## Type of Environmental Trainings

The objectives outlined above, the following types of environmental trainings will be conducted during the AI project.

- Environmental awareness for the project personnel (and other relevant staff of the implementing ministries).

- Environmental training for the EFPs on EMP implementation.

- Environmental trainings on monitoring for zonal M&E coordinators and other monitoring staff

- Environmental awareness and waste disposal trainings for the field teams (ERTs) involved in culling and carcass disposal

- Hospitals/laboratory waste disposal training for the relevant project and MOPH personnel.

- Environmental trainings for the construction staff on waste disposal and other construction related environmental aspects.

Although the above trainings are primarily meant for the project staff, other stakeholders such as the NEPA staff, can also participate in these trainings.

## Training Need Identification and Module Development

The first step in developing the training modules would be to identify the training needs of various personnel.  This process started with the development of present EMP (see Section 1.3), and will continue during the initial phase of the EMP finalization, with the help of additional stakeholder consultations and discussions with the project personnel.

Subsequent to the above step, the training modules will be developed for each type of the trainings listed in Section 7.2 above.  The modules will include the PowerPoint presentations, training handouts, training evaluation forms and trainees evaluation forms.

The training modules for the first five trainings of the above list will be developed by the EWMS, while the one for construction activities will be the responsibility of the construction contractor.

## Initial Trainings

The first three trainings of the list given in Section 7.2 will be conducted by the EWMS, and will essentially be the training of trainers (ToT).  These trainings are expected to be conducted within first three months of the project initiation.  After each training session, a brief report will be developed, which will include the training module, names of the trainees, filled training evaluation and trainees evaluation forms.  These trainings will be repeated as and when needed.

Conducting the environmental trainings for the construction staff will be the responsibility of the respective construction contractor.

## Subsequent Trainings

After the initial trainings (ToT) discussed above, the trained project staff will conduct environmental trainings (4th and 5th trainings in the list given in Section 7.2) for the other staff and relevant personnel from the implementing ministries.  These trainings will be conducted by the EFPs, M&E specialist and zonal M&E coordinators.  These trainings will be repeated on a regular basis; the training schedule will be developed during the EMP finalization stage.

The EWMS when available after the initial 3-month period, will conduct refresher ToTs if a need is felt.

## Environmental Awareness Raising

An important aspect of the avian influenza control strategy is the awareness raising among the stakeholders, particularly the communities keeping domestic poultry.  The project includes development and implementation of a comprehensive communication strategy (Section 3.2.3).  The environmental aspects will be an important element of this strategy.  In this regard, the EWMS will assist the communication specialist in conceiving and designing the environmental component of the strategy.

# Communication and Documentation

This section defines the communication and documentation mechanism for the environmental management of the AI project.

## Objectives

The objectives of the communication and documentation system as part of the present EMP are to systematically document the environmental data and information, communicate it to all concerned, and archive it for future use.

## Communication

### Meetings

The following environmental meetings will take place during the project:

Project initiation meeting(s).

Fortnightly meetings.

The purpose of the project initiation meetings will be to discuss the EMP, and ensure full understanding and commitment from concerned personnel for its implementation.  Separate meetings may be held with construction contractors.

Periodic meetings will be held at site during the entire duration of the project.  The frequency of the meetings will be once in a fortnight, though it can be changed according to the situation.  The meetings will be attended by the project coordinator (optional), M&E specialist, EFPs, EWMS (when available) and any other project personnel if needed.  The purpose of the meetings will be to discuss the EMP implementation, environmental monitoring results, non-compliances noted by the monitoring staff, and any environmental / social issues identified in the field.  The remedial measures will also be discussed and agreed during these meetings.  The meeting will be recorded in the form of an environmental report prepared by the M&E specialist with assistance from EFPs.

### Data Recording and Maintenance

The forms/checklists to be used for recording information during the environmental monitoring will be developed by the EWMS, in consultation with the M&E specialist.  These forms will follow a standard format.  Check boxes will be used as much as possible for ease in filling out the forms and to facilitate data entry.

The filled checklists will be sent to the M&E specialist for further process.

### Grievance Redressal Mechanism

During a disease outbreak and associated culling of birds, the compensation payment may generate community grievances which must be adequately and appropriately addressed for the success of the project.  Towards this end, the compensation procedures (included in the POM) include a grievance redressal mechanism.  Through this mechanism, the community grievances will be recorded, remedial actions, if any, will be determined, responsibility assigned, action take, and the concerned community informed, about the action take.  Complete record will be maintained for all of these steps.

## Documentation

The following environmental reports will be prepared during the project implementation:

Project initiation meeting(s),

Fortnightly meetings,

Environment monitoring.

In addition, the following reports will also be developed during the project implementation:

Complete record of the stakeholder consultations to be carried out during the initial phase of the project (see Section 5.2.2).

Report of each type of trainings conducted by EWMS/EFPs/M&E coordinators.  These reports will include the training modules, names of the trainers and trainees, filled training evaluation forms (to be filled by the trainees), and filled trainees’ evaluation forms (to be filled by the trainers).

These reports will be shared with all the relevant project personnel, and will be available for review by monitoring teams from WB, NEPA or any other stakeholder.

End-of-Project Report:  At the end of the project, an end-of-project report will also be prepared.  It will include summary of the environmental monitoring reports prepared during the project, summary of the environmental trainings, major non-compliances recorded, other key environmental information regarding the project, and recommendations for similar projects in the future.

# Environmental Management Cost

The key elements of the environmental management cost of any project usually include the following:

Cost of environmental personnel

Cost of environmental mitigation measures

Cost of environmental monitoring

Cost of environmental trainings.

These costs for the AI project are discussed below and tabulated in Attachment 9.1.

Environmental Personnel:  The cost of EWMS is included in the overall project cost.  The EFPs will not be available to the project on full time basis, and the existing staff from MOPH and MAIL will be assigned additional responsibilities to perform their responsibilities during the AI project.  Hence their costs are not included in the project cost.

Mitigation Measures:  The environmental mitigation measures will be the integral part of the project implementation, hence these will not incur any additional cost.

Environmental Monitoring:  The environmental monitoring will be implemented through the EFPs, M&E specialist and zonal M&E coordinators.  The cost associated with these personnel is already included in the project cost.

Environmental Trainings:  The environmental trainings will also be developed and conducted by the project staff, as described in Section 7.  These trainings will be conducted in the relevant ministries’ premises, thus incurring no additional cost.

Attachment 9.1:  Environmental Management Cost

| Description | Cost (US $) | Notes |
| --- | --- | --- |
| Environmental Personnel | 72,000 | The indicated cost is for the EWMS. The EFPs’ cost has not been included in the project cost, since they will be the existing employees of the implementing ministries (MAIL and MOPH) and will be available to the project on part time basis. |
| Environmental Mitigation Measures | - | Completely integrated with the overall project cost. |
| Environmental Monitoring | - | Same as above |
| Environmental Trainings | 56,060 | 20% of the total cost for the trainings which will include environmental aspects also (total cost of these trainings included in the project cost: US$ 280,300). |
| Total | 128,060 |  |

# Footnotes

Avian influenza (also called avian flu or bird flu) refers to a group of different influenza viruses that primarily affect birds.  An influenza pandemic happens when a new subtype emerges that has not previously circulated in humans.  If H5N1 adapts into a strain that is contagious among humans, it will no longer be a bird virus but a human influenza virus.

A National Avian Influenza Committee (NAIC) was established as soon as the Minister MAI confirmed the existence HPAI (H5N1).  Membership of NAIC includes MAI, Ministry of Public Health (MOPH), Ministry of Commerce (MOC), Ministry of Finance (MOF, and the Ministry of Environmental Protection (MEP), representatives of concerned donors and implementing organizations such as FAO, USAID, USDA, EU, ADB, WB, WHO and UNICEF.

Article 1 of the Environmental Law (unofficial English translation).

Synonymous to Environmental Impact Assessment (EIA) or Environmental and Social Assessment (ESA).

The waste disposal guidelines will be applicable to other similar facilities as well.

Source:  Interim Guidelines for Managing Potential Environmental and Social Safeguard Issues in Bank-assisted Avian Influenza Control Project.  Quality Control and Assurance Unit.  World Bank.  April 2006.

Table adopted from the one provided in the Technical Annex of the project documentation.

Details on bio-safety in microbiological and biomedical laboratories can be found at the CDC website http://www.cdc.gov/od/ohs/pdffiles/4th%20bmbl.pdf and guidelines for environmental infection control in health-care facilities (recommendations of cdc and the healthcare infection control practices advisory committee - hicpac) can be found at http://www.cdc.gov/mmwr/preview/mmwrhtml/rr5210a1.htm

http://www.who.int/csr/resources/publications/biosafety/Biosafety7.pdf

Guidance on culling, decontamination, worker protection, disposal of carcasses, and other containment procedures for HPAI and other highly infective zoonotic diseases, as appropriate, are available through the following recommended references: fss.k-state.edu/research/books/carcassdisp.html ,    http://www.defra.gov.uk/animalh/by-prods/publicat/dispguide.pdf , http://www.oie.int/downld/AVIAN%20INFLUENZA/A_GH_CARCASS.pdf ,  http://www.fao.org/DOCREP/004/y0660E00.htm , http://www.osha.gov/Publications/OSHA3114/osha3114.html,  http://www.osha.gov/dsg/guidance/avian-flu.html ,   http://www.animalhealthaustralia.com.au/shadomx/apps/fms/fmsdownload.cfm?file_uuid=D4552211-C369-9A31-F51B-3DB61D0CCB39&siteName=aahc , http://www.animalhealthaustralia.com.au/aahc/index.cfm?E9711767-B85D-D391-45FC-CDBC07BD1CD4#ops , http://www.oie.int/eng/normes/mcode/en_chapitre_3.6.1.htm , http://www.oie.int/eng/normes/mcode/en_chapitre_3.7.6.htm , http://europa.eu.int/comm/food/animal/diseases/controlmeasures/avian/directive_avian_en.pdf

Details on biosafety in microbiological and biomedical laboratories can be found at the CDC website http://www.cdc.gov/od/ohs/pdffiles/4th%20bmbl.pdf and guidelines for environmental infection control in health-care facilities (recommendations of CDC and the healthcare infection control practices advisory committee - HICPAC) can be found at http://www.cdc.gov/mmwr/preview/mmwrhtml/rr5210a1.htm

For detailed guidance on laboratory waste, refer to the WHO Biosafety Guide at: http://www.who.int/csr/resources/publications/biosafety/Biosafety7.pdf

For detailed guidance on medical waste, refer to the WHO/WB document “Better Health Care Waste Management” at: https://www.who.int/water_sanitation_health/medicalwaste/bhcwmeng.pdf, as well as the updated procedural guidelines developed for the MENA region and jointly published by WHO and the World Bank in 2005, including training materials on medical waste management.

FIDIC, the International Federation of Consulting Engineers (the acronym stands for the French version of the name) represents globally the consulting engineering industry and promotes internationally accepted construction standards for works – details can be found at http://www.fidic.org/

The EWMS will be available to the project on an intermittent basis: for total six months during the entire project duration of three years.

Frequency of meetings may be adjusted per the situation.

All of the costs in this table are already included in the total project cost (Chapter IV of Project Operations Manual).

# Text boxes

E1457